Biodiversity Heritage Library Quarterly Report

August 1 – October 31, 2011

First Quarter, Fifth Project Year

- Introduction/Executive Summary

The Scanning and Digitizing Component continued to ramp up scanning with a total of 94,900 volumes consisting of 35, 320,000 pages as of October 31, 2011.  Permissions for digitizing 179 publications within copyright, mostly significant serial runs,  have been obtained from several publishers. BHL conducted a user survey and is working on implementing the recommendations. Digital Object Identifiers were assigned to some out-of-print monographs in the BHL Portal. Planning for the Global BHL meeting and the Life and Literature Conference proceeded.

- Technical Report

- Operations

- Management or staff transitions -

The BHL Program Director,  Tom Garnett's, salary has been covered by the Smithsonian Institution Library since August 1.

- Operations coordination

- Staff activities (covered below under multiple other categories)

- Strategic direction

- Progress toward milestones – (see attached metrics).

- Subsequent quarter goals and metrics -

The milestone “Leverage crowd-sourcing” with the metric of “number of articles deposited” (in Citebank) is under review at present.  The publishers and Authors Guild lawsuit against Google has altered the intellectual property landscape and previous counsel about “safe harbor” protection for user uploaded content may need to be revisited and reviewed.   BHL staff at the Missouri Botanical Garden and the Smithsonian ran a small pilot with an individual who did the due diligence for obtaining permissions for individual articles, scanning them, and sending for ingestion into Citebank.   While the pilot was successful in the sense that the content was loaded into CiteBank and the permissions were given where necessary, the approach is not scaleable.

- Improving internationalization

- International outreach and activities

Invitations went and acceptances were received for the Global BHL Planning meeting from colleagues at BHL-Australia (Museum Victoria), BHL-China (Institute of Botany, Chinese Academy of Sciences), BHL-SCIELO Brasil (SCIELO), BHL-Europe  (MNH and Museum fur Naturkunde, Germany).  The partner projects worked to build an agenda for the November meeting.

- Agreements/MOUs

After several meetings exploring areas of mutual interest, the United States Geological Survey Library has signed the MOU to join the BHL Institutional Council.  The USGS Library has many biodiversity collections that will augment the BHL and has a strong record of digital projects and technical excellence.

- Increasing content

The Scanning and Digitizing Component continued to ramp up scanning with a total of 94,900 volumes consisting of 35, 320,000 pages as of October 31, 2011.  Permissions for digitizing 179 publications within copyright, mostly significant serial runs,  have been obtained from several publishers.

- Content contributions

- Content related activities

- Improving the user experience

The BHL Technical team released new features that make it easier for users to create their own articles. (Users are currently ~80 per day). Drawing from the functionality provided by colleagues on the BHL-Australia web site, http://bhl.ala.org.au, they added the ability for users to review the page selections before they generate a PDF.  Users now also have the opportunity to review the title, author and/or keyword data they have provided and make any necessary corrections/edits.  BHL staff surveyed some of the most active PDF creators and received positive feedback about these changes and many good ideas about changes that could be made for the future.

- Tool design and requirement analysis

Coordinated by Chris Freeland, BHL Technical Director, BHL staff conducted a useability  study comparing BHL-US and BHL-Australia sites.  The study revealed that each site has functionality the other lacks and clarified the steps needed to bring them into alignment.  Simon Scherrer, the BHL-Australia UI designer has been invited to the Missouri Botanical Garden to meet with technical staff to work on this.

- Tool implementation

After  months of discussion with CrossRef, BHL has finally been successful in assigning DOIs to digitized monographs in BHL.  As a meaningful, yet somewhat cheeky example, we chose Linnaeus' Species Plantarum, 1753, as our first assignment:
http://dx.doi.org/10.5962/bhl.title.669
DOIs are resolvers, so clicking on that link will resolve you to the page in BHL for Sp. Pl.:
http://www.biodiversitylibrary.org/bibliography/669 
In the short term BHL will begin mass assignment of the remaining DOIs.  This will allow BHL metadata to be exposed to publishing industry indexers, and will hopefully drive traffic from new sources.  In the longer term we'll investigate how we can use CrossRef's bibliometrics to determine who is linking to our research and determining ways of improving the service overall.

- Engaging the wider scientific community

i.	Scientific outreach

- Partnerships and projects

Martin Kalfatovic, BHL Deputy Director and Chris Freeland, BHL Technical Director attended several Digital Public Library of America (DPLA) meetings to explore alignment between the two programs.

- Letters of support (see Testimonials at end)

- Engaging education and citizen science communities

- Public outreach

BHL technical staff upgraded the functionality of the BHL Portal with social media icons that make it easier to share BHL content with others.

- Learning tools

- Education modules

- Improving EOL’s impact, engagement and reputation

- Publications and websites

"The Biodiversity Heritage Library: Advancing Metadata Practices in a Collaborative Digital Library." Joseph M. deVeer, John F. Furfey, Martin R. Kalfatovic, Matthew A. Person and Suzanne C. Pilsk. Journal of Library Metadata 10(2010), 136-155

- Presentations

Chris Freeland, BHL Technical Director, presented at the Sherbourn Symposium.  Tom Garnett was invited to lead a section of the Internet Archives Leaders Forum in San Francisco in September relating to governance based on his BHL experience. Tom Garnett attended a USGS sponsored workshop on a new program, Biodiversity in Service to Our Nation (BISON).  This workshop won that national prize for the the most contorted and artificial acronym in 2011.

- Building the new open linked library: Theory and Practice Joel Richard, Trish Rose-Sandler, Keri Thompson. LITA Forum 30 September 2011. St Louis, MO.

- Crowdsourcing the creation of articles within the BHL Bianca Crowley and Trish Rose-Sandler. LITA Forum 01 October 2011. St Louis, MO.

- Meetings, workshops, and conferences

Chris Freeland, BHL Technical Director, and Martin Kalfatovic, BHL Deputy Director attended the Biodiversity Standards Organization (TDWG) meeting in New Orleans.

- Achieving financial sustainability

- Fundraising efforts

Donate to BHL feature on the BHL Portal. As part of the initial redesign of the BHL site, there is now a “Donate to the BHL” button allowing individuals to immediately support the BHL. These transactions are processed through the Smithsonian Institution Libraries' (SIL) financial system.

- Financial Report

- Budget explanation

The subaward for scanning at the New York Botanical Garden has been completed and closed out.  The subaward for scanning at the American Museum of Natural History is completed but not yet closed out.  The subward for the Marine Biological Laboratory will be be completed by February, 2012.  The subaward for the San Francisco Academy of Science will be completed by January 2012.  The subward for the Missouri Botanical Garden is current.  All invoices submitted to date have been paid or are being processed for payment.

- Financial report (attached)

- Appendices

- Metrics spreadsheet

- Other

The number of EOL species pages with links to BHL texts: 1171663. The number that have no other data except the BHL links: 741684.  12,162,061 BHL text pages link to EOL species pages.

CiteBank update.  See attached report.

bhl-europe report – see attached.

sil bhl report – attached.

Testimonials

Monday, September 12, 2011
From Louis Diringer, via gmail [mailto: louis.diringer@wanadoo.fr]

Dear Grace Costantino,

Thank you so much for replying me so quickly and efficiently.

Of course, I do understand that copyrighted works cannot be freely available without explicit permission from the right holders.

I do really appreciate what you did for letting me have a private access to this paper I was looking for a long time. I'd like to take the opportunity to let you know how much the Biodiversity Heritage Library Librarian initiative is highly appreciated among people like me who try to learn from those who delivered valuable information in the past. Your website is a real treasure! Congratulations.

Please do again accept my sincere and warmest thanks

Best regards


Louis DIRINGER


Thursday, September 1, 2011
From Shelia Connor, via feedback gmail [mailto: sheila_connor@harvard.edu]

Dear Grace,
It works just fine now, perhaps I was being too impatient. I love and use BHL ALL THE TIME! SEE http://arboretum.harvard.edu/library/arboretum-publications/
Sheila

Tuesday, August 30, 2011
From Ling Li, via Gemini (mailto: lingli@mit.edu]

This is a great source!!!

Thursday, August 18, 2011
From Dan Noreen, via Gemini [no email given]

Wow! You are awesome! Thanks so very much for your incredible quickness and efficiency in downloading the article I have been seeking for ages. Best wishes, Dan Noreen

Friday, August 12, 2011
From Mike Augee, via email to Bianca [mailto: fossil@well-com.net.au]

Dear Bianca,

We have heard from a number of people who have used your site to access our back issues. It is a great contribution to world science, and I for one greatly appreciate it.

Best Regards,
Mike Augee
Editor
Proc Linn Soc NSW

Tuesday, August 9, 2011
From Liz Edwards, via Gemini [mailto: elizabeth. edwards@noaa.gov]

No questions or problems, just a Thank You comment for creating such an incredibly useful technological marvel!

Thursday, August 4, 2011
From Derek Butcher, via Gemini [mailto: tillands@bigpond.com]

Dear Grace
Pleased to hear that. I don't know if you realise that this facility of yours is the best thing since sliced bread for we Aussies. To get easy access to old journals is fantastic and I have a great time ( in my retirement) in researching Bromeliaceae. You may even have bumped into an Uncle Derek on the ether! >:-}
Derek

Wednesday, August 3, 2011
From M K Janarthanam, Ph.D via email forwarded from Martin. [mailto: mkjana@yahoo.com]

Dear Chris,
It was pleasure meeting you and listening to your talk on BHL. Moreover, BHL forms the backbone of of whatever little work we do. Thanks to you all, without your efforts getting literature would have been daunting task for us.

I discussed the matter with the Secretary of Indian Association for Angiosperm Taxonomy (publisher of Rheedea) and he was excited though he needs to get formal approval from Executive Committee. We will start the process and contact you. We did scan volumes up to vol 18, but the quality was not good. If required we can ship hard copies. From vol. 19 we have soft copies (pdf). 

Regarding other resources that could be part of BHL - we need to take stock and prioritise and locate the resources. Few libraries that harbor them are yet to see the purpose.

Shall get back to you soon.

regards,
jana


Tuesday, August 2, 2011
From Les Landrum, via Gemini [mailto: les.landrum@asu.edu]

THIS IS A WONDERFUL SERVICE! Thank you! Les Landrum, ASU

Tuesday, August 2, 2011
From @ISF_NatSci via Twitter

"You got a great website...:-)"