BHL-China Quarterly Report

The 4th quarter 2011

Fenghong Liu, Zheping xu, Jinzhong Cui

- Introduction:

This report covers the 4th quarter of 2011 (2011-10-01 through 2011-12-31). In this quarter, BHL-China finished scanning the old books collected in the Library of Institute of Botany (the sponsor institution of BHL-China) the number of which was approximately 5000 copies. In Nov., 2011, the journal scanning was started. That means that the content of BHL-China was expanded.

In older to strengthen the connection between BHL-USA and  BHL-China, the team members, Drs. Cui Jinzhong, Xu Zheping and Liu Fenghong visited USA in the middle of Nov., 2011. The both sides deeply discussed the standard of metadata of scanned items, the copyright handling and the scanning workflow, etc in the Smithsonian Institution. BHL-China team took part in the 2nd Global BHL meeting and Life and Literature Conference in Chicago. In the Missouri Botanical Garden, how to share data between BHL-USA and BHL-China, how to transfer the metadata of the items of BHL-China (from CNMARC to MARC21 ), how to use the name finder tool of Ubio were discussed.

In Dec., 2011, sub-project of the National Herbarium Platform, the biodiversity literature digitizing, was launched. This sub-project is an extension of BHL-China and will be still focusing on how to preserve the valuable literature in the field of diversity in a digital way. And more a scanning facility will be set up required by the sub-project.  Also, BHL-China began scanning the books outside of the Institute of Botany.

- Content Statistics:

Approximately 2,200 new items with 400,000 pages were scanned in the throughout three months. The BHL-China received 4 scanning requests and they were fully met. Besides, BHL-China OCRed 12 volumes with 10,000 pages of China Higher Plant (Fu Liguo, Qingdao Publisher, 1999-2011), more than 8,000 scientific names and over 5,000 Chinese names were extracted from which.

- Website Statistics

- The detailed information of website statistics can be seen the special website statistics table and figures which are provided along with the quarter report.

- Anecdotes and Testimonials

- This sort of anecdote is really related to BHL-USA. There is a special service provided by member libraries of the Chinese Academy of Sciences (which hosts more than 150 research institutes located around China), literature delivery, meaning the reader could get the literature which he wants for from any the member library only if the library collects one in demand.  Normally, the librarian scans or copies the literature and then posts it to the reader. Now, if the literature in demand is related to biodiversity and being out of copyright, the librarian just search it from the homepage of BHL-USA firstly. About 8 researchers got the literature in this way during this referred quarter.

- About BHL

- BHL-China, in alignment with the Global BHL, aims to digitize Chinese literature of biodiversity and related fields and establish an easy-searchable platform to make the literature easily accessible.  Scientific community is the first audience of BHL-China. Meanwhile, BHL-China is dedicated to data sharing among the global BHL nodes. Furthermore, BHL-China is closed related with biodiversity informatics related projects, such as China Virtual Herbarium, China Field Museum, Catalogue of China Higher Plants, Species-2000 etc. and  is committed to provide service literature and data source (especially description, distribution information of species) to them.