| Deliverables List |  |  |  |
| --- | --- | --- | --- |
| Deliverable No | Deliverable title | Delivery date | Who |
| 1 | D2.1 Catalogue of content holder requirements (quality, quantity, accessibility, standards and specifications of content and metadata) | M 3 | Bernard Scaife |
| 2 | D3.1 Deliver composition of Technology Management Board and initial meeting | M 3 | Adrian Smales |
| 3 | D5.1 Web site, including multimedia presentation | M 3 | Jiri Kvacek |
| 4 | D5.2 BHL-Europe newsletter and mailing list | M 3 | Jiri Kvacek |
| 5 | D5.3 Database of relevant conferences/events and ownership for BHL-Europe presentations | M 3 | Tine Mallaerts |
| 6 | D5.4 Deliver composition of Communications Working Group and 1st dissemination plan | M 3 | Jiri Kvacek |
| 7 | D1.1 Progress Report 1 | M 6 | Henning Scholz, Jana Hoffmann |
| 8 | D3.2 Document agreed standards, best practice and system components | M 6 | Walter Koch, Kai Stalmann |
| 9 | D3.3 Plan for managing interoperability issues, data harmonisation and the integration of the content into BHL-Europe, EUROPEANA and the BHL | M 6 | Adrian Smales, Kai Stalmann, Julie Verleyen, Chris Freeland |
| 10 | D5.5 BHL-Europe dissemination plan | M 6 | Jiri Kvacek |
| 11 | D5.6 BHL-Europe promotion kit | M 6 | Jiri Kvacek |
| 12 | D2.2 Prototypes of deduplication tool and bibliographic database system for monographs and serials | M 9 | Tom Gilissen, Kai Stalmann, Bernard Scaife |
| 13 | D3.4 Implement plans for all components in WP3, incl. data models, technology standards etc. | M 9 | Roger Essoh, Adrian Smales |
| 14 | D4.1 Delivery of IPR working documents, including best practice guide, due diligence guide, pro forma agreements and process for formally agreeing rights management with rights holders. Complete agreement with EUROPEANA and BHL for reciprocal access and Rights metadata. | M 9 | Nancy Chillingworth, Lizzy Komen, Tom Garnett |
| 15 | D1.2 Progress Report 2 including pre-financing request | M 12 | Henning Scholz, Jana Hoffmann |
| 16 | D1.3 Annual Report 1 including first ideas for BHL-Europe business plan | M 12 | Henning Scholz, Jana Hoffmann, Graham Higley/Tom Garnett |
| 17 | D2.3 Prototype of Web-database for content management and collection analysis | M 12 | Kai Stalmann, Bernard Scaife, Tom Gilissen |
| 18 | D2.4 Content analysis and management status report 1 (metadata, page numbers, content providers) | M 12 | Kai Stalmann |
| 19 | D3.5 Technical architecture status and progress report with particular focus on the development of the German prototype | M 12 | Adrian Smales, Roger Essoh, Walter Koch |
| 20 | D5.7 Online questionnaires for user survey | M 12 | Jiri Kvacek |
| 21 | D5.8 First user evaluation report | M 15 | Jiri Kvacek |
| 22 | D1.4 Progress Report 3 | M 18 | Henning Scholz |
| 23 | D3.6 Release German prototype | M 18 | Adrian Smales, Walter Koch, Chris Freeland |
| 24 | D1.5 First overview of the business plan for long-term sustainability | M 24 | Henning Scholz, Tom Garnett, Adrian Smales |
| 25 | D1.6 Progress Report 4 including pre-financing request | M 24 | Henning Scholz |
| 26 | D1.7 Annual Report 2 | M 24 | Henning Scholz |
| 27 | D2.5 Final and enhanced Web-database for content management and collection analysis | M 24 | Kai Stalmann, Bernard Scaife, Tom Gilissen |
| 28 | D2.6 Delivery of the first version of the approved best practice guidelines and standards | M 24 | Kai Stalmann, Adrian Smales |
| 29 | D2.7 Content analysis and management status report 2 (metadata, page numbers, content providers) | M 24 | Kai Stalmann |
| 30 | D3.7 Key components documented for output of D3.5 e.g. BHL-Europe Portal, OCR demonstrators, distributed storage model, etc. | M 24 | Adrian Smales, Roger Essoh, Walter Koch |
| 31 | D4.2 Complete signed agreements with first group of rights holders to enable material to be used in the BHL or EUROPEANA, and establish process for addition of further material. | M 24 | Nancy Chillingworth |
| 32 | D4.3 Deliver IPR framework to support long-term access and sustainability of the digitised material | M 24 | Nancy Chillingworth |
| 33 | D1.8 Progress Report 5 | M 30 | Henning Scholz |
| 34 | D3.8 Sustainability policy for continuation of service e.g. hosting, future development, helpdesk provision for service users/content providers etc. | M 30 | Adrian Smales, Chris Freeland, (Heimo Rainer) |
| 35 | D5.9 Second user evaluation report | M 30 | Jiri Kvacek |
| 36 | D1.9 Business plan for long-term sustainability | M 36 | Henning Scholz, Tom Garnett, Adrian Smales |
| 37 | D1.10 Implementation of results of BHL-Europe in other projects | M 36 | Henning Scholz, Tom Garnett, Jiri Kvacek |
| 38 | D1.11 Progress Report 6 and Final Report including Financial Statement | M 36 | Henning Scholz |
| 39 | D1.12 Final Report | M 36 | Henning Scholz |
| 40 | D2.8 Content analysis and management status report 3 (metadata, page numbers, content providers) | M 36 | Kai Stalmann |
| 41 | D2.9 Delivery of the final revised best practice guidelines and standards | M 36 | Kai Stalmann, Adrian Smales |
| 42 | D3.9 Live BHL-Europe system, with distributed storage and management and appropriate tools for the continued development of services and ingress of multilingual content | M 36 | Adrian Smales, Chris Freeland, Kai Stalmann |
| 43 | D5.10 BHL-Europe multimedia presentation, final version | M 36 | Jiri Kvacek |
| 44 | D5.11 Illustrated book on best practice guidelines and standards for the public | M 36 | Kai Stalmann, Adrian Smales, Jiri Kvacek |