Biodiversity Heritage Library Quarterly Report

February 1-April 30, 2013

Third Quarter, Sixth Project Year

- Introduction/Executive Summary

The Biodiversity Heritage Library collection now constitutes 59,679 titles and 112,867 volumes, comprising 40,722,204 pages in BHL (April 2013).  Permissions for digitizing 273 publications within copyright, mostly significant serial runs, have been obtained from 125 licensors.

BHL has approved new vision, mission, and goal statements. The BHL Vision: “Inspiring discovery through free access to biodiversity knowledge.” The BHL Mission: “The Biodiversity Heritage Library works collaboratively to make biodiversity literature openly available to the world as part of a global biodiversity community.” BHL has five goals, including:

Goal 1: Relevant Content

Build and maintain the BHL as the largest reliable, reputable, and responsive repository of biodiversity literature and archival materials.

Goal 2: Tools and Services

Develop services and tools which facilitate discovery and improve research efficiency of BHL content.

Goal 3: User Engagement

Increase global awareness about the BHL through outreach, learning and education, and branding through engagement and collaboration with existing and new user communities.

Goal 4: Membership and Partnerships

Grow BHL consortia membership and partnerships while fostering cross-institutional collaboration that continues to serve as a model for digital library development.

Goal 5: Financial Sustainability

Ensure sustainability and relevance by being flexible, adaptable, and financially sound while the content and services remain openly and freely available.

On March 18, 2013, the new BHL interface launched. The new interface includes an updated design; article and chapter level access to content; API, OpenURL, and Data Export enhancements; book viewer updates; and an improved PDF creation process.  A new name finding algorithm, capable of identifying previously undiscovered taxon names, has also been implemented. Test applications of this algorithm on a portion of the BHL corpus have already resulted in an increase in nearly 50 million name instances in BHL, translating to over 20 million new unique names identified.

In other project news, BHL released its thirteenth and fourteenth iTunes U Collections, including “Notable Women in Natural History” and “Connecting Content through Archival Field Notebooks;” published the Winter 2013 BHL Newsletter and Q1 and Q2 FY13 Quarterly Reports; and celebrated the BHL-Africa launch on April 15, 2013. Furthermore, the 2013 BHL Institutional Council Meeting occurred May 6-7, 2013, in Woods Hole, MA. Topics discussed included the approval of the 2013 Dues Budget; approval of the BHL vision, mission and goals; proposed updates to the BHL membership structure; and fundraising possibilities. Finally, BHL received two significant awards, including the Charles Robert Long Award of Extraordinary Merit from the Council on Botanical and Horticultural Libraries (CBHL) and IDG's Computerworld Honors Program Laureate.

In financial news, to date BHL has raised $228,589.60 in dues and donations for project sustainability. Finally, BHL submitted a report on the 2012 BHL Program costs and revenue raised. Total project costs for 2012 were $2,038,975.87 and total funds raised in 2012 for BHL were $2,287,410.81. SIL subsidized 90% of the BHL Secretariat costs (BHL Program Director, Manager and Collections Coordinator and associated central administrative costs), and Missouri Botanical Garden subsidized 68% of the Technical Team costs (BHL Technical Director, Developer, and Data Analyst and associated technical costs).

- Technical Report

- Operations

- Management or staff transitions

Last quarter, we reported that the Library of Congress joined BHL at the Steering Committee level, thus constituting the fifteenth BHL member library. On Thursday, March 28, 2013, Nancy Gwinn, Grace Costantino, and Elizabeth O'Brien (Smithsonian Libraries Director of Marketing and Special Events) visited the Library of Congress for a ceremonial signing of the MOU with Roberta Shaffer (Associate Librarian for Library Services, LoC) and Leslie Girard (Confidential Assistant to the Associate Librarian for Library Services, LoC).

This quarter, we’re pleased to announce that the American Museum of Natural History has upgraded their membership to the Steering Committee level. Steering Committee membership requires annual dues of $10,000 but entitles participating members to input on BHL’s budget and operations, as well as use of the pan-BHL Scanning money (see “Operations Coordination” for more information).

In February, 2013, Jacqueline Chapman joined the Smithsonian Libraries as the new BHL Librarian, replacing JJ Ford who accepted a position at the Smithsonian's Astrophysical Observatory in Cambridge in January, 2013. Chapman is in charge of managing SIL’s BHL digitization workflow as well as helping to coordinate scanning requests among BHL member institutions.

- Operations coordination

In compliance with the BHL governance structure, regular conference calls for the BHL Executive and Steering Committees continue, as well as the maintenance of listservs for both of these groups and the Institutional Council. Calls discuss operational activities and project coordination. Wiki pages for the management and support of activities performed within these groups are also maintained. Executive Committee calls occur on a weekly basis, while Steering Committee calls occur the fourth Thursday of every month.

Monthly BHL Staff Calls also continue, hosted by BHL Collections Coordinator, Bianca Crowley. These calls discuss project and workflow coordination among BHL’s partner institutions.

BHL Program Manager, Grace Costantino, continues to manage an extensive BHL calendar system to assist in project, conference, and editorial coordination. It is available to all staff members, and staff are encouraged to contribute events to the calendar.

Smithsonian Staff are currently working with the Library of Congress and Internet Archive to implement a new Internet Archive scanning contract. The current contract expires at the end of May. The new contract will initiate a new pricing structure and will be used to manage funds for SIL as well as pan-BHL scanning activities (see below).

The initial pot of $10,000 allocated towards pan-BHL scanning has been spent. These funds supported the digitization of approximately 100,000 new pages for BHL. Funds were used to digitized “priority” titles – titles identified as high impact content for BHL users based on impact factors and TL2 and Index Animalium citations. These funds come from a portion of the Steering Committee Dues. Members of the Steering Committee may use these funds, which are managed through the Smithsonian Internet Archive FedLink account, to scan books from their libraries at their local IA centers.

As part of the 2013 BHL Institutional Council Meeting, the BHL Steering Committee approved the addition of $25,000 to this pan-BHL scanning workflow, for use throughout the rest of 2013. These funds will be released as soon as the new Internet Archive scanning contract is in place. (See “Achieving Financial Sustainability” for more information on budget)

- Staff activities (covered below under multiple other categories)

- Strategic direction

The BHL Steering Committee has approved a new vision, mission and goals for BHL.

BHL Vision: Inspiring discovery through free access to biodiversity knowledge.

BHL Mission: The Biodiversity Heritage Library works collaboratively to make biodiversity literature openly available to the world as part of a global biodiversity community.

Goals:

Goal 1: Relevant Content

Build and maintain the BHL as the largest reliable, reputable, and responsive repository of biodiversity literature and archival materials.

Goal 2: Tools and Services

Develop services and tools which facilitate discovery and improve research efficiency of BHL content.

Goal 3: User Engagement

Increase global awareness about the BHL through outreach, learning and education, and branding through engagement and collaboration with existing and new user communities.

Goal 4: Membership and Partnerships

Grow BHL consortia membership and partnerships while fostering cross-institutional collaboration that continues to serve as a model for digital library development.

Goal 5: Financial Sustainability

Ensure sustainability and relevance by being flexible, adaptable, and financially sound while the content and services remain openly and freely available.

Since September, 2012, BHL has been in the process of revising our vision, mission and goals. As part of the 2012 Staff and Technical Meeting, staff began brainstorming elements for a new vision statement and goals, as well as provided themes for incorporation into a new mission statement. After the meeting, two staff working groups organized to further flesh out the vision and goal statements. In March 2013, the BHL Secretariat reviewed the input provided by staff to produce final draft vision, mission and goal statements.

As part of the 2013 BHL Institutional Council Meeting (see “Meetings, Conferences and Workshops” for more information), the BHL Steering Committee reviewed these drafts statements, provided slight edits, and approved the statements as official. The vision and mission were incorporated into the BHL homepage, and the Goals are prominently displayed on the BHL About page, linked from the homepage of the website.

As part of our continued strategic planning, BHL Collections Coordinator Bianca Crowley, with assistance from the BHL Secretariat and select staff members, has compiled a Projects and Initiatives document for BHL. This document captures all BHL tasks currently underway, planned for the future, or suggested for the future. It organizes these tasks according to the new BHL goals. This document will serve as the single organizational hub for tracking BHL work and ensuring that work performed not only meets the strategic direction of the project, but is prioritized according to overall project priorities. Priorities from this document will be used to draft 2-year workplans for BHL. The Secretariat will manage this document, and all proposed future tasks for BHL must be incorporated into this document and aligned with overall project goals.

- Progress toward milestones – (see attached metrics spreadsheet)

- Subsequent quarter goals and metrics

The milestone “Leverage crowd-sourcing” with the metric of “number of articles deposited” (in Citebank) is under review at present.  We are entering a new phase in Citebank development (See “Tool Design and Requirement Analysis” for more information). We are working to merge Citebank into the BHL portal. All Citebank functionality, and the delivery of article content, will be available via the BHL portal. A rough target date for this implementation is June, 2013. Due to these transitions, we are suspending Citebank metrics reporting until the application is available in BHL, at which time we will determine the appropriate statistics to gather. For more information on Citebank development and our plans for the project, see “Citebank 1 Pager.”

It has been decided that BHL will not pursue a safe harbor model, allowing users to upload their own PDFs to BHL. All content to BHL must come through implemented workflow processes and be provided by BHL member institutions, ingested from Internet Archive, or contributed in collaboration with publishers.

Finally, due to difficulties obtaining the precise number of pages re-hosted by partner projects, this metric has been adjusted to the number of items re-hosted by partner projects, i.e. global partners. The YR 5 Goal for items rehosted by partner projects was calculated by taking the previous page goal and dividing by the average number of pages in a book, 300, resulting in a YR 5 Goal of 116,700 items. Due to delays in the rewrite process, the YR 5 global rehosting goal has not been achieved, thus, the YR 5 Goal remains in place as the YR 6 Goal.

- Improving internationalization

- International outreach and activities

The BHL-Africa officially launched during a ceremony hosted by the South African National Biodiversity Institute (SANBI) at the Pretoria National Botanical Garden in Pretoria, South Africa on April 15, 2013. Over two dozen representatives from institutions that have either signed or intend to sign the BHL-Africa MOU were present. Additionally, six US BHL colleagues were invited to attend. A two-day workshop followed the launch, focusing on such topics as governance, collaboration, communication, outreach, and digitization workflow.

The BHL-Africa Steering Committee was also elected at the meeting. BHL-Africa has been divided into three regional nodes: North/Central; Eastern; Southern. Each regional node elects two representatives for the Steering Committee. Currently, there is no representation in North/Central Africa within the project, so only four members (two from Southern, two from Eastern) were elected at the meeting. Elected members include: Anne-Lise Fourie (SANBI, Southern); Ria Groenewald (University of Pretoria, Southern); Ashah Owano (National Museums of Kenya, Eastern); and Loi Namugenyi (Uganda National Council for Science and Technology, Eastern). Lawrence Monda (National Museums of Kenya) was elected as the BHL-Africa Technical Representative.

BHL-Africa will contribute digitized texts to the main BHL portal. An installation of Macaw, which allows users to upload content digitized outside of the Internet Archive workflow for ingestion into IA and BHL, has been installed at the University of Pretoria. As a virtualized installation, staff at BHL-Africa institutions throughout the continent will be able to log-in to the Pretoria installation to upload their scans to BHL through IA.

BHL-Australia continues to contribute digitized texts to the BHL project via the Macaw software as well. To date, BHL-Australia has contributed 64,778 pages to BHL via this method. Work to merge the BHL-US/UK portal and the BHL-Australia portal designs and functionalities is also complete. See “Tool Implementation” for more information.

BHL Europe Director Henning Scholz has accepted a new position with Europeana and has left BHL Europe and the Berlin Natural History Museum. A new BHL-Europe Director, and a new Global-BHL Vice-Chair, have yet to be appointed.

Due to these changes, development on the GRIB (or the Global Reference Index to Biodiversity, which was to serve as a workflow management tool that could be utilized by all global BHL partners) has been suspended. There are now no plans to implement this tool, and BHL partners will continue using existing de-duplication tools to manage scanning coordination.

BHL-Brazil continues to contribute citations to BHL’s article repository, Citebank. These citations link back to full-text PDFs available on the BHL-Brazil website. To date, 7,177 citations from BHL-Brazil have been added to Citebank.

To date, BHL’s global partners have contributed 363,402 pages to the BHL portal. BHL’s global partners contributing content include BHL-Australia, BHL-Europe, and BHL-China.

- Agreements/MOUs

BHL continues discussions with the California Digital Library, and has entered into discussions with the National Agricultural Library, regarding BHL membership. As mentioned in “Management and Staff Transitions,” Library of Congress and the American Museum of Natural History have joined BHL at the Steering Committee level.

As part of the 2013 BHL Institutional Council Meeting (see “Meetings, Conferences and Workshops” for more information), a group was formed to update the BHL membership document. This document outlines requirements and guidelines for new BHL members. Discussions also occurred regarding revising BHL’s membership structure. Further considerations in this area will occur within the BHL Executive Committee.

- Increasing content

BHL collections now constitute 59,679 titles and 112,867 volumes, comprising 40,722,204 pages in BHL (April 2013).  Permissions for digitizing 273 publications within copyright, mostly significant serial runs, have been obtained from 125 licensors.

- Content contributions

- Content related activities

Contribution to the BHL Flickr account continues, with 73,449 images currently added to the collection. The Flickr account pulls out the amazing natural history illustrations from BHL books and serves them up to users in an easy, approachable manner. It continues to be one of the most popular services offered by BHL, and has instigated a great deal of discussion about providing better access to BHL illustrations.

In February, 2012, BHL launched the Biodiversity Heritage Library on iTunes U, consisting of collections of select BHL material centered on such themes as “Extinct Species,” “Rarest of the Rare,” “Charles Darwin’s Library,” and “Theodore Roosevelt.” New iTunes U collections are released on a quarterly basis. This quarter, BHL released two new iTunes U collections: Notable Women in Natural History and Connecting Content through Archival Field Notes.

The Notable Women in Natural History collection features selected works created by women who made direct contributions to the study of Botany and Zoology either by way of authoring or editing works on the subject or by providing critical illustrations to support the works authored by someone else. It was created to coincide with Women’s History Month in March.

The Field Notes collection was created in collaboration with the Connecting Content project. This project, an IMLS National Leadership grant-funded undertaking, aims to digitize published scientific findings, their related field books and specimens, and metadata for these items, link all of these resources, and make them available for harvesting, reuse, and repurposing without cost. At this point, the bulk of the field books selected for this project (61 titles in all) have been digitized and made available through the Biodiversity Heritage Library. The iTunes U collection features a select portion of these titles.

The Biodiversity Heritage Library now has its own collection of images in the Encyclopedia of Life. This collection is comprised of images that have been tagged with species name machine tags. EOL periodically harvests tagged images from the BHL Flickr for inclusion in the EOL collection. The collection currently holds 2,742 images representing 3,349 taxa, and will continue to grow as additional illustrations are tagged in the BHL Flickr. These harvested images are uploaded to EOL with a non-trusted status, allowing EOL curators to decide whether the species name tags associated with the images are correct.

BHL has now implemented the ability to support articles. Using algorithms developed by Rod Page of BioStor, a selection of BHL content has been broken down to individual articles and parts, which are indexed and searchable on BHL. Furthermore, a new tab in the advanced search screen allows users to search for specific articles. The BHL book viewer also includes a new Table of Contents tab, which allows users to see the articles indexed within the book being viewed. In BHL’s back-end, an upgrade allows staff to manually break down BHL books into articles or chapters as well.

- Improving the user experience

We continue to collect and promptly respond to user-submitted feedback for BHL. This feedback includes questions, comments, alerts about problems with BHL content, requests for items to be scanned and added to the collection, and, happily, praise from our users. All feedback (called ‘tickets’) is collected via an issue tracking system (called Gemini), and users receive answers to their feedback within 24 hours of receipt. This feedback is directly used to improve content and services on BHL. To date, we’ve received over 5,309 user-submitted tickets. For more feedback statistics, see attached “Gemini Report.”

In September, 2012, BHL also began officially gathering statistics on the number of pages manually paginated for the BHL project. Though minimal pagination is asserted at the time of scanning by the scanner, this metadata is usually confined to general page numbers and an indication of the title page. In order to designate issues, articles, and images and plates within BHL scanned content, staff must manually apply these augmentations. From February-April, 2013, BHL staff manually paginated 116,628 pages.

- Tool design and requirement analysis

Staff at Smithsonian Libraries have begun gathering requirements and have set aside funds for the creation of a complete copy of BHL content on Smithsonian servers, which we hope to have in place by the end of CY13.

It has been decided that Citebank, BHL’s previous article repository, will be merged into BHL. Citebank currently houses user-created PDFs and some PDFs contributed by users that were uploaded by BHL staff. Staff hope to have Citebank merged into BHL end of calendar, 2013. As mentioned in “Strategic Direction,” as a result of these changes, we are suspending Citebank metrics gathering until further notice. Find out more about our plans for Citebank in “Citebank 1 Pager.”

- Tool implementation

The new BHL user interface launched on March 18, 2013. The new interface includes:

- Updated Design: The website's design has been upgraded to reflect the celebrated aesthetics of the BHL-Australia portal.

- Article and Chapter Access: The ability to search BHL by article or chapter titles has been implemented. To date, over 92,000 articles and chapters have been indexed and are searchable within BHL. Additional articles and chapters will become available as the collections continue to be indexed (see “content related activities” for more information).

- Open Data Enhancements: BHL's APIs, OpenURL interface, and Data Exports have been modified to include available article and chapter information.

- Book Viewer Updates: The BHL book viewer has been updated, allowing users to view multiple columns of pages on screen at once and more easily navigate to a specific page within a book. Users can also view OCR text alongside page images, and, where the books have been indexed, users can navigate directly to the articles or chapters within.

- PDF Creation Improvements: The custom PDF creation process has been improved, allowing users to select pages for their PDF while in the book-viewer mode and more easily review the PDF before creation.

In March, BHL outreach staff implemented a wide-scale publicity campaign announcing the release of the new website to the public. This included two blog posts, one published two weeks before the launch and the other published the day of the launch, a press release on the day of the launch, and weekly tweets and Facebook posts, beginning in late February, counting down to the release. Staff also developed User Instructional materials to guide users through the changes.

BHL has actively collected user feedback regarding the new UI and has implemented several updates and fixes based on information received. These include:

- Adding the ability to download the OCR for selected pages alongside images in BHL custom PDFs

- Incorporating the contributing library into the book viewer

- Fixing a bug in the PDF generator that did not allow PDFs to be created if only some article information was submitted

- Adding the ability to zoom within the custom PDF creation process

- Updating the search result display to make it more obvious to users that search results are arranged according to content type (in beta)

BHL technical staff have also implemented a new taxon name finding algorithm capable of identifying previously undiscovered taxon names throughout the BHL corpus. Test applications of this algorithm on a portion of the BHL corpus resulted in an increase in nearly 50 million name instances in BHL, translating to over 20 million new unique names identified.

As mentioned previously, SIL BHL staff have developed a software called Macaw that allows users to upload content scanned outside of the Internet Archive workflow into IA so that it can be ingested into BHL. Two remote installations of Macaw have been implemented: one at the Missouri Botanical Garden for use in the Art of Life project, and another at the University of Pretoria in South Africa (see “International Outreach and Activities” for more information). Smithsonian Libraries is currently working with OCIO to set up a third remote installation at SIL that can be used by partners in the US and the UK to upload content to BHL.

- Engaging the wider scientific community

i.	Scientific outreach

In order to engage with our scientific community, and understand how they use BHL and what they need from BHL, we continue to publish a monthly blog series entitled “BHL and Our Users,” in which we feature a different user in each post and interview them about their work and how they use BHL to support that work. Though not exclusively featuring scientific users, a majority of the user base interviewed are scientists.

DOIs (Digital Object Identifiers) assigned to BHL content allows us to track usage originating from users clicking on citations to BHL content in external sources. Each DOI resolution translates to a visit to BHL and represents a baseline for how much traffic comes to BHL because users cite our collections. This past year, we have had 79,441 DOI resolutions.

BHL was highlighted in the following five recent publications for its contributions to scientific research:

- Marhold K, Stuessy, T (2013) The Future of Botanical Monography: Report from an International Workshop, 12-15 March 2012, Smolenice, Slovak Republic. Taxon. 62 (1): 4-20.

- Seltmann KC, Pénzes Z, Yoder MJ, Bertone MA, Deans AR (2013) Utilizing Descriptive Statements from the Biodiversity Heritage Library to Expand the Hymenoptera Anatomy Ontology. PLoS ONE 8(2): e55674. doi:10.1371/journal. pone.0055674.

- Ang Y, Puniamoorthy J, Pont AC, Bartak M, Blanckenhorn WU, Eberhard WG, Puniamoorthy N, Silva VC, Munari L, Meier R (2013) A Plea for Digital Reference Collections and Other Science-based Digitization Initiatives in Taxonomy: Sepsidnet as Exemplar. Systematic Entomology. doi: 10.1111/syen.12015.

- Robert JR, Drost, CA (2012) Biodiversity Heritage Library. College & Research Libraries News. 73 (10): 626-627.

- Bieler R, Petit RE (2012) Molluscan Taxa in the Publications of the Museum Godeffroy of Hamburg, with a Discussion of the Godeffroy Sales Catalogs (1864-1884), the Journals des Museum Godeffroy (1873-1910), and a History of the Museum. Zootaxa 3511: 1-80.

- Partnerships and projects

BHL is serving as a content hub for the Digital Public Library of America, which launched on April 18, 2013. As a result of BHL’s participation as a digital content hub, links to over 111,000 BHL volumes will be available within the DPLA portal. Through the DPLA, the Biodiversity Heritage Library will collaborate with renowned libraries, universities, archives and museums to reach a wide national audience.

Progress on the Field Notebooks project, funded by an IMLS grant, continues, with digitization of field notebooks and specimens underway at many partners, and soon to be underway at others. 61 Field notebook titles scanned by BHL consortium members are currently available in BHL. Learn more about the publicity campaign BHL hosted for Field Notebooks in “Public Outreach.”

BHL staff at Cornell University and New York Botanical Garden have engaged in a project to digitize seed catalogs held in botanical collections around the country. The catalogs digitized by BHL member institutions may ultimately be ingested into the BHL corpus.

- Letters of support (see Testimonials at end)

- Engaging education and citizen science communities

- Public outreach

Social media activities continue in full swing. BHL is active on the following platforms: Facebook, Twitter, Flickr, Pinterest, and the blog.

Twitter: To date, we have 2,716 followers on Twitter

Facebook: To date, we have 5,325 Page “Likes” on our Facebook account

Flickr: To date, we’ve added 73,449 images to our Flickr account

Pinterest: To date, we have 3,101 images and 16 collections on Pinterest

Blog: This quarter, we’ve had 10,818 visits to our blog, and our regular series “Book of the Week” and “BHL and Our Users” continue to be very popular

For more social media metrics, please see “BHL Q2 FY13 Quarterly Report”: http://biodivlib.wikispaces.com/file/view/BHL%20Q2%20FY13%20Quarterly%20Report.pdf/433005724/BHL%20Q2%20FY13%20Quarterly%20Report.pdf

BHL received two prestigious awards this quarter, including the IDG Computerworld Laureate and the CBHL Long Award for Extraordinary Merit.

In March, BHL was named a 2013 Computerworld Laureate for excellence in using information technology to promote positive social, economic, and educational change. Founded by the International Data Group in 1988, the Computerworld Honors Program celebrates innovative IT achievements. Program Awards will be presented at the Gala Evening and Awards Ceremony on June 3, 2013.

The Biodiversity Heritage Library also received the Charles Robert Long Award of Extraordinary Merit from the Council on Botanical and Horticultural Libraries (CBHL). The highest honor bestowed by CBHL, the Long Award was founded to honor outstanding contribution and meritorious service to CBHL or to the field of botanical and horticultural libraries or literature. Since 1988, only 14 people have received this award. Receiving two separate nominations highlighting BHL’s global collaboration among libraries, innovative outreach, and exceptional bibliographic and technology standards, this year marks the first time an organization has won the award.

Program Manager, Grace Costantino, continues to collaborate with colleagues at the National Museum of Natural History, submitting weekly tweets linking to BHL content for publication on the @NMNH twitter account and NMNH Facebook account. She also works with EOL staff to post a weekly BHL post to the EOL Facebook page and several tweets related to BHL on the EOL twitter feed each week. These tweets are regularly retweeted by the public, and Facebook posts on these collaborators’ pages regularly receive 100+ likes and shares.

This quarter, BHL also actively collaborated with the American Museum of Natural History, California Academy of Sciences, and the Smithsonian to promote various outreach content.

BHL continues to launch its quarterly newsletter, which provides project highlights via email subscription. To date, 678 people have subscribed to the newsletter. In February, the Winter Newsletter launched, with a 46% open rate.

The Q1 and Q2 FY13 BHL quarterly reports are now available:

Q1: http://biodivlib.wikispaces.com/file/view/BHL%20Q1%20FY13%20Quarterly%20Report.pdf/414998418/BHL%20Q1%20FY13%20Quarterly%20Report.pdf

Q2: http://biodivlib.wikispaces.com/file/view/BHL%20Q2%20FY13%20Quarterly%20Report.pdf/433005724/BHL%20Q2%20FY13%20Quarterly%20Report.pdf

BHL Program Manager Grace Costantino is drafting a detailed BHL Communication and Outreach plan that articulates the audiences we will reach and the platforms we will use for BHL outreach. The plan also describes special strategies for organizing outreach content and growing the BHL audience. A final draft of the plan will be submitted to the BHL Steering Committee for review in July 2013.

As structuring BHL outreach activities around week-long "campaigns," in which all outreach via social media centers around a particular theme, has proven very successful at increasing traffic to our social media outlets and to BHL from these outlets, BHL Outreach staff have scheduled Outreach Campaigns through July, 2013. BHL hosted the following campaigns this quarter:

| Campaign Title | Campaign Dates | Description |
| --- | --- | --- |
| Women's History Month | March 4-8 | BHL celebrated Women's History Month with a campaign in March, which included an iTunes U collection entitled "Notable Women in Natural History." BHL highlighted women and resources related to these women in BHL, and posted about these figures and content via Twitter and Facebook. We also prepared a Flickr collection of images from works related to notable women. Sandra Knapp, expert on Jeanne Baret, contributed a guest blog post for the campaign, and Becky Morin of CAS wrote a piece on Mary Anning for later in March. |
| Audubon | April 22-26 | Celebrating Audubon's birthday with a campaign dedicated to his life and works in BHL. Campaign included Tweets, Facebook posts, and a Blog Post dedicated to Audubon materials. |
| Field Notebooks | May 6-10 | In May, BHL celebrated field notebooks in collaboration with Connecting Content staff. Digitized field books from Connecting Content have been ingested into BHL, and staff created an iTunes U collection. This collection, and its relationship to BHL publications, was highlighted through Tweets and Facebook posts. Yolanda Butos of the CAS Connecting Content project wrote a blog post for the campaign, and staff from the Smithsonian's Field Book project collaborated with BHL staff to write four blog posts related to field books and associated publications, which published from February-May. |
| Curious and Bizarre Creatures of Nature, Myth, and Legend | May 20-24 | In May, BHL will celebrate publications highlighting curious and bizarre creatures, many of which are labeled as “monsters.” The campaign highlights the weird, strange, and downright scary books in BHL. Tweets, Facebook posts, a blog post, and a Flickr collection highlight this content. Grace Costantino interviewed Lilla Vekerdy, Head of SIL Special Collections, about a rare book featuring “monsters” to highlight in the blog post. This campaign will run in conjunction with Animal Planet’s “Monster Week,” and will utilize the #monsterweek hashtag to gain new followers. |

On April 2, 2013, BHL hosted a third tagging party at the Smithsonian, in conjunction with both the Encyclopedia of Life and Smithsonian's Ocean Portal. This time, the event focused on a theme: Marine Biodiversity. For tagging parties, BHL and EOL invite Smithsonian staff, including curators, volunteers, interns, fellows, and librarians, to gather in person for an hour and a half to help add species name tags to BHL Flickr images in a group setting. Since this was a themed event, staff directed attendees to specific sets of marine images in need of tagging. The 17 people that attended the party made some good headway on the thousands of marine images that need tagging.

- Learning tools

BHL-Europe staff have developed the Biodiversity Library Exhibition tool, an application that allows staff to build virtual exhibitions around specific themes. This tool allows staff to curate collections of BHL materials and augment these resources with related images, stories, and factoids. Built on a Drupal platform, BHL-E released this platform to the larger BHL community in conjunction with the workshop held at the 2012 TDWG conference in Beijing. This quarter, BHL-Europe released their latest exhibit, Nature at Your Home, which incorporates many BHL texts. Grace Costantino worked extensively with BHL-Europe staff to promote this new exhibition. BHL staff in the US are currently brainstorming ways to utilize BLE for their own educational outreach activities.

As mentioned in the “Content-Related Activities” section, BHL staff are working to develop supplemental iBooks for teachers incorporating BHL content around educational themes. A draft of the first BHL iBook, dedicated to Shark Week, has been completed by Smithsonian Libraries BHL Technician, Gilbert Borrego. BHL and EOL have had discussions about collaborating on future iBooks to incorporate content from both projects.

From March 4-8, BHL hosted its first pan-BHL intern, Irina Zeylikovich - an alternate spring break intern from the University of Michigan School of Information. With a focus on BHL outreach, Irina performed environmental scans of comparable digital library social media efforts and identified popular topics for BHL outreach. She also began developing a system to help organize outreach efforts.

BHL has also named three additional summer interns. The first two are BHL Marketing interns, which will build further on the work done by Irina to support outreach activities. The third intern is a BHL virtual reference intern, which is currently working to help coordinate scanning requests across BHL member libraries.

- Education modules

- Improving EOL’s impact, engagement and reputation

- Publications and websites (See final page of Report)

- Presentations (See final page of Report)

- Meetings, workshops, and conferences

The seventh annual BHL Institutional Council Meeting occurred at the Marine Biological Laboratory and Woods Hole Oceanographic Institute Library (MBL-WHOI) in Woods Hole, MA, on May 6-7, 2013. Representatives from eight member libraries were able to attend the meeting in person, and, for the first time in IC Meeting history, those who could not be present physically were able to virtually join the meeting using video conference software available within the MBL-WHOI library. As part of the meeting, the 2013 BHL Dues budget was approved; BHL’s new vision, mission and goals were approved; possible changes to the membership structure were discussed; and fundraising opportunities were suggested.

See “BHL Presentations” below for more details on presentations given this quarter.

- Achieving financial sustainability

- Fundraising efforts

BHL has raised $10,521.60 in donations to date, which are processed through the Smithsonian Libraries' financial system. The allocation of these funds is decided by the BHL Steering Committee.

To date, BHL has raised $218,068 via Steering Committee Dues, from 13 member institutions in 2013 and 9 member libraries in 2012, for future development. These funds are annual dues contributed by those BHL member institutions that wish to be a part of the BHL Steering Committee, allowing them to vote on project decisions and fund allocations.

The BHL Steering Committee approved the spending budget for the BHL Dues. Spending categories include Technical Director salary support, hardware and software funds, application of DOIs, server storage support, Internet Archive scanning (including $25,000 in pan-BHL scanning funds – see “Operations Coordination” for more information), travel and meeting costs, and outreach materials. Grace Costantino sends out monthly spending reports for Dues and Donations money.

As part of the 2013 BHL Institutional Council Meeting, a BHL Fundraising group was formed to discuss possible fundraising opportunities for BHL, including creating a BHL product store and implementing print on demand features.

SIL staff received confirmation on the FY13 Federal Allocation for BHL, which will amount to $125,000.

Martin Kalfatovic and Grace Costantino met with Tina Morrison and Tina Muracco (SIL Development Staff) to discuss future fundraising ideas for BHL. Ideas which will be pursued include creating BHL products to send as “thanks yous” to donors contributing a minimum donation; allowing users to sponsor collections on BHL; holding themed fundraising campaigns; creating a map to showcase locations around the world where donations have come from; and creating a thank you video to display when users submit donations via the webform.

BHL submitted a report on the 2012 BHL Program costs and revenue raised. Total project costs (including member library costs and central services - Secretariat and Technical Team; excluding Harvard Botany and Missouri Botanical Garden Library, which were unable to submit their contributions) for 2012 were $2,038,975.87. Total funds raised in 2012 for BHL were $2,287,410.81. SIL subsidized 90% of the BHL Secretariat costs (BHL Program Director, Manager and Collections Coordinator and associated central administrative costs), and Missouri Botanical Garden subsidized 68% of the Technical Team costs (BHL Technical Director, Developer, and Data Analyst and associated technical costs).

- Financial Report

- Budget explanation

The subawards for scanning at the New York Botanical Garden, the American Museum of Natural History, the Marine Biological Laboratory, and the California Academy of Sciences have been completed and closed out. The subaward for the Missouri Botanical Garden is current, and an extension until May 31, 2013, has been received. All invoices submitted to date have been paid.

- Financial report (attached)

- Appendices

- Metrics spreadsheet (attached)

- Other

The number of EOL species pages with links to BHL texts: 1,208,119. Number of EOL species pages that have no other data except the BHL links: 3,547. Number of BHL text pages that link to EOL species pages: 15,370,118.

BHL Q2 FY13 Quarterly Report:

http://biodivlib.wikispaces.com/file/view/BHL%20Q2%20FY13%20Quarterly%20Report.pdf/433005724/BHL%20Q2%20FY13%20Quarterly%20Report.pdf

Gemini February-April, 2013 – attached

BHL Website Analytics - Attached

- Testimonials (for “Letters of Support”)

- Wednesday, April 24, 2013

  - Via Twitter, from @mrvaidya

  - “Bless the @BioDivLibrary, whoever figures out all the acronymic forms of journal names, and whoever paginates their articles.”

- Monday, April 22, 2013

  - From Scott Miller, via Gemini

  - “Thank you so much for this service. Let's see, a journal written in 1773/1774, published in 1908, and long out of print. I love that I get to read it. Okay, so here's my suggestion: Keep up the excellent work.”

- Tuesday, April 16, 2013

  - From Tönu Talvi, via Gemini

  - “Dear Biodiversity Library, I would like thank you all very much for invaluable work and support you do. I am just downloaded/got pdf-file from more than century old (1893) journal paper (regional naturalistst society paper, published in Finland). To get copy I should take 500 mile drive to our university library. Now I am got it fastly in high-quality pdf-copy. Cordial thanks and all success in continuing your highly valuable mission.”

- Wednesday, April 10, 2013

  - From Sue Gibb, via Gemini

  - “Congratulations! Although I use BHL a lot in the course of my work, I had come to dread using it as searching had became cumbersome and time-consuming. This new search system is brilliant. I love it. Thanks!”

- Tuesday, April 9, 2013

  - via Twitter, @infodocket

  - “The Superb Biodiversity Heritage #Library Will Be a DPLA Content Hub ow.ly/jToJ3 #dpla #bhl @BioDivLibrary”

- Monday, April 8, 2013

  - via Twitter, @sedgeboy

  - “@BioDivLibrary - just used your new website to select & download an article to my tablet. Definitely a nice improvement, congrats!”

- Thursday, April 4, 2013

  - Via Twitter, @SxBRC

  - “More beautiful works or natural history art and illustration from @BioDivLibrary here: j.mp/12kWdxc. Simply glorious.”

- Thursday, April 4, 2013

  - Patternbank suggests using BHL images for pattern and graphic inspiration: http://patternbank.com/album-de-aves-amazonicas-biodiversity-heritage-library/

- Thursday, March 28, 2013

  - From, Lucinda Crecca, via gmail

  - “I am in heaven when I had found the Biodiversity Heritage Library web site. Access to the old books is wonderful. This is what I expected the Internet to be when it started, access to books and museums information access. Not all the dumb games and shopping. And I really do not want everyone in the world to know what I am doing every hour of the day like in face book and twitter, sorry I am old school. The Biodiversity Heritage Library web site is great because there a allot of us who do not live in a big city where you can go to the museums and libraries, at least I did live in NYC for my first 22 years and was able to visit them then Once again thank you for all your help.”

- Thursday, March 28, 2013

  - Via Facebook, Joan Young

  - “I do Biodiversity Research and Education and have just discovered you page. Love what you have on it.”

- Monday, March 25, 2013

  - From: Laurie Hannah, via gmail

  - “Hi Bianca, We are really excited to see our publications online! Thanks so much. And yes, I did see your new interface last week, as I needed to download an article. It's great and really works well. I love BHL!!!”

- Monday, March 25, 2013

  - Via Twitter, @Nick_MasOnMar

  - “@BioDivLibrary New site looks great! #bhlib”

- Friday, March 22, 2013

  - From Paul Subhajit, via gmail

  - “Hello, I use Biodiversity Heritage Library frequently. I do not have a credit card. In India, it is difficult to pay online overseas with a debit card for some banking restrictions. I think many people like me would gladly donate a little amount if you make such arrangement so that paying in Indian currency with a debit card become possible just like Wikipedia have done from previous year.”

- March 21, 2013

  - Via Flickr: Subject: Just wanted to say Thank You.

  - “Hi BioDivLibrary, I just wanted to say thank you for posting such wonderful botanical prints. Whenever I open my Flickr home page I always see something new from you and I usually wander over to your photostream to take a better look. Invariably I spend quite a while marveling at the prints that you post and I wanted to pass along a huge thank you for taking the time to scan and post continuously. I, for one, enjoy your posts immensely.”

- Tuesday, March 19, 2013

  - Praise on our blog post: http://blog.biodiversitylibrary.org/2013/03/announcing-new-biodiversity-heritage.html

  - BHL-Europe said: “Congratulations for a new great User Interface and functionalities!”

- Monday, March 18, 2013

  - Comment on blog from Divyaraj Shah

  - “Loved the new BHL !! Keep it up guys :) :) Its a great project!!!”

- Monday, March 18, 2013

  - Article about the new website by Rod Page: http://iphylo.blogspot.com/2013/03/new-look-biodiversity-heritage-library.html

- Monday, March 18, 2013

  - Via Twitter, @kristenlans

  - “@BioDivLibrary Looking good!”

- Friday, March 15, 2013

  - Article using BHL images: http://blogs.scientificamerican.com/culturing-science/2013/03/15/deextinction/

- Friday, March 15, 2013

  - via Twitter, from @tammy_horton

  - “@echinoblog h/t to the ever wonderful @BioDivLibrary where I got it...

  - in response to:

  - echinoblog: “h/t to @tammy_horton for that BHL link!”

- Thursday, March 14, 2013

  - Comment left on blog post: http://blog.biodiversitylibrary.org/2013/03/a-consortium-that-scans-together-bands.html

  - “The Asiatic Society journal is a truly amazing work and its founder James Prinsep was equally so. As a private researcher, a species loathed in India especially by government officials, the BHL has been the only source that allow access to these materials readily. Unfortunately a couple of issues are still unavailable, unfortunately my attempt to find the missing issue failed but will post it when I do. I do wish some of the Indian libraries and archives would have the vision to join hands with you. There are apparently some amazing book collections at the Zoological Survey of India, the Bombay Natural History Society and so on unfortunately they do not consider it worth having archivists or subject matter specialists among their library staff (ie. with a science background that allows them to appreciate literature).”

- Wednesday, March 13, 2013

  - Via Twitter, @Flic_Anderson

  - “Discovered you can search species names in entire @BioDivLibrary! Guessing I'll be responsible for spike in 3am GMT "Teucrium" searches! :D”

- Wednesday, March 13, 2013

  - From Jennifer Scheibling, via Gemini

  - “Dear BHL, First off, kuddos! Your site is amazing and I love to spend time browsing around through all of the wonderful, old natural history texts. What I enjoy the most though are the wildlife prints that can be found in the different texts. I have been unable to figure out a way to search for a particular species and have a list brought up that pinpoints what pages of what texts have images of these species on them. Is there some sort of image search that I'm missing that would allow me to do this without having to view every single page that has a particular species mentioned on it? If not, that would definitely be a feature worth adding - that would make an amazing site all the more stellar.”

- Friday, March 8, 2013

  - From Hélène Dumas, via gmail

  - “Dear Grace, I thank you for your efforts. It's really great for amateurs as I am to have open access to publications via the Biodiversity Heritage Library.”

- Thursday, March 7, 2013

  - Feedback on Blog Post "The Perfect Holiday Gift,” from Brenda Gioia

  - “I would be more than willing to purchase these intricately designed postcards especially after knowing that it part of the money will go to environmental programs. I'm always a fan of this kind of craftsmanship.”

- Wednesday, March 6, 2013

  - Via Facebook, in regards to new interface, from Pj Johnson

  - “aaaaiiiiieeeee. . . BHL withdrawals!! Can't wait `til the 18th! need, need, need. . ., writhing in agony. . .”

- Wednesday, March 6, 2013

  - Feedback sent to Tom Baione (AMNH) from Frieda Sutton

  - “Dear Tom, I met you a few weeks ago (early in February) while on a fabulous tour of the library as part of my interview day with the Richard Gilder Graduate School. I had told you how helpful I found the Biodiversity Heritage Library when writing my undergraduate senior thesis, and you asked that I send you a bit about my experience with the database. Here goes: For my thesis project, I wanted to compare scientific literature on classification of tarsiers (a primate group) from before and after the cladistics revolution. I was looking for a very specific and somewhat obscure symposium from 1919 to use as my pre-cladistics platform, and miraculously, I was able to find it online! Through the BHL, I was able to download pdf files and text of the pages I wanted from the symposium ("Proceedings of the Zoological Society of London, 1919") and search through the pages with ease. Often, I would be looking for just a keyword to link me to an idea or person and I could easily find it with just a quick search of the documents downloaded from the database. I must say, I am greatly indebted to BHL. I honestly do not know if my thesis project would have been possible without it. At the very least, it made my research significantly easier. I'm happy to know that there are resources and people out there that are committed to digitizing and making available scientific literature, old and new.”

- Monday, March 4, 2013

  - Praise for BHL on Tumblr: http://carlzimmer.tumblr.com/post/21324371176/a-hornbill-from-an-1882-monograph-i-could-look-at

  - “A hornbill from an 1882 monograph. I could look at this Flickr stream of old nature prints all day. (by BioDivLibrary)”

- February 28, 2013

  - Via Facebook, from Antonio Lavelli

  - “What of awesome page ... I'll follow you with interest; congratulations!”

- Prominent mention of BHL in Taxon Article:

  - "The Future of Botanical Monography: Report from an international workshop, 12-15 March 2012, Smolenice, Slovak Republic." Taxon. 62 (1), February 2013: 4-20.

- February 28, 2013

  - From Christopher Geissler, via gmail

  - “Dear Ms. Costantino, Thank you so much for your thorough reply. I was speaking to a colleague at the Sterling and Francine Clark Art Institute who mentioned that some of their recently digitized holdings had made it into the BHL. We were both excited to see it. Thank you again.”

- February 27, 2013

  - BHL to be credited in upcoming publication:

  - “I will include a thank you to BHL, and the web site address, in the acknowledgments of our invited review paper (O. Oftedal and D. Dhouailly, "Evo-devo of the mammary gland", Journal of Mammary Gland Biology and Neoplasia): ‘We greatly appreciate the assistance of staff at the Smithsonian Institution Libraries, and at the History of Medicine Division of the US National Library of Medicine, in locating physical copies of old embryological publications, and thank the Biodiversity Heritage Library for online access (www.biodiversitylibrary.org/) to scans of such works.’”

- February 26, 2013

  - From Dr. Chris Thompson, via gmail:

  - “I love the BHL. I may have the finest private library on flies (Diptera), but now while I have a copy, I find it faster, easier, etc., to go to the BHL and get the page I want, rather than stepping into the next room and pulling my own copy off the shelf and then going back to make copy of that page.”

- February 26, 2013

  - From Olav Oftedal, via gmail

  - “Dear Grace Constantino, Thank you very much. This was my first download, but I am thrilled with what I have been able to find re: archaic mammary embryology some of which I had been hoping to find at the National Library of Medicine, and to get it through your program was a huge advantage. Last night I believe I requested and received 11 PDFs, all of which are essential to a review paper I am completing, and I had no problems. I had even decided that my problem with this file may have been that it was so big, so I requested it as two parts (A and B) and received those individually without problem. Of course the entire publication in one file was better, so thank you very much.”

- 24 February, 2013

  - via Flickr

  - “Hi Bianca, The images have been created and uploaded. Check them out on my photo-stream http://www.flickr.com/photos/67312941@N03/8504225098/in/photostream/! Thanks for uploading such a valuable resource and for all your hard work as a collective initiative.

- Thursday, February 21, 2013

  - Mention of BHL in The Public Domain Review: http://publicdomainreview.org/2012/12/27/engravings-from-history-of-the-earth-and-animated-nature-1825/

- Wednesday, February 20, 2013

  - PLOS Article using BHL: http://www.plosone.org/article/info%3Adoi%2F10.1371%2Fjournal.pone.0055674#abstract0.

- Wednesday, February 20, 2013

  - Mention of BHL in webcast on Food Fight Show.org (mention by Anthony Goddard of EOL about 15 minutes in)http://foodfightshow.org/2013/02/saving-the-world-with-devops-big-data-and-hpc.html

- Wednesday, February 20, 2013

  - From Prof. Dr. Hartmut H. Hilger, via gmail

  - “BHL is great! Thanks and regards”

- Saturday, February 16, 2013

  - via Twitter, from @echinoblog

  - “@BioDivLibrary Today I used OCR to find some terminology usage in the old literature! MUCH easier than trying to find it by hand! thank you!”

- Thursday, February 14, 2013

  - From Toby Musgrave, via gmail

  - “Hey Grace, Nice to be in touch again and I hope you are doing well. Thanks for the update, I can't say enough how useful BHL is! I am spreading the word all opportunities I get!”

- Wednesday, February 13, 2013

  - Via Twitter, from @IArtLibraries

  - “What are your favorite @Pinterest boards to follow? I think @BioDivLibrary and @ALALibrary are my fave. :-)”

- Tuesday, February 12, 2013

  - Via Twitter, from @adammarre

    - “@BioDivLibrary the BEST.”

  - Via Twitter, from @AMlibrari

    - “Looking for genus or species name refs? Use @BioDivLibraryAdvanced Search, Scientific Names bit.ly/Z8PvMW Good stuff!”

  - Nice blog post that mentions BHL: http://www.geekosystem.com/darwin-day-2013/

    - “Then again, there’s a strong argument for celebrating Darwin Day like an academic, poring over old tomes, decoding margin notes and taking a scholarly approach to the celebration. While it doesn’t necessarily sound like our idea of a great time, we think Darwin would approve. He’d probably be especially flattered if you went to the Biodiversity Heritage Library to look through digitized versions of the books that made up Darwin’s extensive library, complete with a guide to notes in each one made by the godfather of evolution himself.”

- Tuesday, February 12, 2013

  - From Charles McNett, via Gemini

  - “Thanks so much for the download of Bradshaw Hall. So simple!!!”

- Tuesday, February 5, 2013

  - From Sarah Sulick, on the BHL Flickr

  - “I second those quotes from the crowd (i.e., I'd like to wallpaper my house with these. Biodiversity Heritage Library's Flickr stream; I've been spending this gray, uninspiring weekend playing w/Pinterest & machine-tagging Flickr images from @BioDivLibrary). I used BDL’s images as table markers and place cards for my wedding a few years ago. And plan to use some to decorate my soon to arrive baby’s room!”

- Tuesday, February 5, 2013

  - From Hermann Falkenhahn, via Gemini

  - “Hello colleagues I am an entomologist and taxonomist and I've been downloading quite a bulk from your fantastic website for noncommercial (scientific) purposes. Being quite abroad from the nearest library your website helps enormous to get all the (many) sources needed for thorough in-depth literature study. Without your service I would be forced to almost live in a library for weeks (my home is quite abroad). I am working on a bibliography on holarctic Lepidoptera, actually.”

February-April 2013 BHL Presentations: