Encyclopedia of Life Scanning and Digitizing Component Quarterly Report

For the period November 1 – January 31, 2011

Executive summary: The Scanning and Digitizing Component continued to ramp up scanning with a total of 87,700 volumes consisting of 32,600,203 pages as of February 1.  Permissions for digitizing 129 publications within copyright, mostly significant serial runs, have been obtained from several publishers.  More are under discussion.

Progress

- BHL China Chris Freeland, Martin Kalfatovic and Keri Thompson attended technical meetings related to the Biodiversity Heritage Library China node, November 15-17, 2010. The meetings, held at the Institute of Botany, Chinese Academy of Sciences (Beijing) took place over three days and covered scanning workflow, operation of the Internet Archive Scribe machine, technical standards for ingesting BHL-China materials into the BHL portal site, and replicating BHL data on IB/CAS servers. BHL China program director Dr. Jinzhong Cui led the meetings. Also attending from BHL China were Fenghong Liu (project coordinator and Director of the Institute of Botany Library), Zheping Xu (technical director), and Shao Qing representing the Institute of Botany. 
Additional presentations from the Institute of Botany staff included Chen Bin discussing the building the Chinese Field Herbarium, Li Min, project director for the Plant Photo Bank of China (PPBC), and a detailed presentation on the data storage systems in place at the Chinese Academy of Sciences. The BHL team also received a tour of the Institute of Botany Library, source of materials for the initial scanning project.

- Bianca Crowley, Grace Costantino, and Chris Freeland, BHL-US staff, traveled to London for the latest BHL-Europe meeting on December 1-3, 2010.  The main subjects comprising this recent meeting were workflow, technical issues and portal development, and the Global References Index to Biodiversity, also known as the GRIB. The intent of the GRIB is to serve as a single point of access to all biodiversity bibliographic records held within the library catalogues of the BHL-EU partners, which will in turn link to digitized versions of the content. The GRIB will also function as a selection and de-duplication tool for all BHL partners, allowing institutions to indicate which items they wish to scan while also providing digitization status information.  A wish to contribute to the development of the GRIB by providing insight into the workflow management tools currently in use on the project was a main purpose of BHL-US staff’s involvement in the meetings. By explaining how staff currently use the many tools necessary for scanning workflow in the US, and what specific tasks staff need a master workflow management tool to address, BHL-EU was able to understand the requirements of their partners across the Atlantic, and development of the GRIB was positively impacted by the conversations.  The meetings were a productive exercise in communication and collaboration, and served as an excellent opportunity to get to know colleagues that, until the meeting, were known only through emails and occasional Skype calls. As BHL continues to expand around the world, it is hoped that such cooperation will continue, and that we will all work together to share our experience, learn from our collective mistakes, and in general provide a better digital library to the users that depend so heavily on our resources for access to the biodiversity literature of the world.

- The latest global partner, BHL SciELO, from Brazil was officially launched on December 1st, 2010 in a public event at the Museum of Zoology of the University of Sao Paulo, BHL-South America is implemented by the Scientific Electronic Library (SciELO) Program. Sharing BHL's open access practices, they maintain an online multidisciplinary collection of quality journals which will total more than 700 titles by the end of this year.  The BHL-SciELO launching event included scientific programming that shared information and experiences regarding challenges and next-steps for the BHL-SciELO Network Project. Abel L. Packer, Biodiversity Research Program Coordinator, spoke in depth about advancements already achieved and laid foundations for the next 3 years of work. Prominent Brazilian biodiversity related libraries will digitize their collections in the coming years according the principles, methodologies and procedures of the BHL and SciELO network.  An MOU has been sent for review and signing.

- CiteBank was launched in early December. The initial services include Upload and storage of digital files associated with citations and  Automatic ingest of service-enabled publishers, digital libraries, and institutional repositories.  Sources included crowd-sourced pdfs from the Portal, SciElo metadata from our Brazilian partners, ZooKeys, and others were loaded.  Statistics below.

- BHL has used name finding algorithms that analyze all of the scanned pages in BHL and extract out the scientific names within. This functionality was released in 2007 and has received minor enhancements in usability. To date more than 81 million potential name strings have been identified by the TaxonFinder algorithm, representing 1.6 million unique names. A new interface to these data has been moved into production, giving users enhanced functionality in using BHL's names-based bibliography. Users can now sort records within the results returned, and the results can be exported into a variety of popular reference manager formats including BibTex, EndNote, and a simple CSV file.

- BHL has a new look and improved functionality. As a result of user feedback received from the BHL survey and through our feedback form we have improved the BHL interface. Gone are the days of the subject keyword tag-cloud on the BHL homepage. Today, the new interface provides a variety of tabs to facilitate simple or advanced search strategies.
• Search is given more emphasis – search is now the central focus of the home page. Users can start with either a general search or more advanced search easily just by clicking additional tabs.
• more Advanced Search options – users can now search one or more fields within a book or journal (e.g. title, author, volume, language, etc)
• search by Series – series statements are now searched when searching a book or journal. These statements are also included in the search results when available.
• search by Citation – individual citations can now be searched via the Citation Finder tab. This feature uses the BHL’s OpenURL resolver to search for individual pages in books and journals.
• Browse and Search are now more consistent – browse and search pages and search results are now consistent in appearance and functionality. For example, users can now more easily sift through a long list of search results by sorting results either by title, author, or year
• CSV download option - Books/Journals search results are now downloadable as .csv format.

- In November The Biodiversity Heritage Library, added more than 14,000 bibliographic metadata records of digitized materials to WorldCat, making these items accessible to researchers through the world's largest resource for finding library materials.  Tom Garnett was quoted in the press release, “A cooperative relationship with OCLC directly advances this key objective. Additionally, the metadata is now available for libraries to use locally through OCLC to integrate into their workflow.”  WordCat is a global network of library-management and user-facing services built upon cooperatively-maintained databases of bibliographic and institutional metadata. WorldCat enhances productivity across the full range of library workflows—from cataloging to resource sharing to discovery and delivery—by intelligently reusing contributed data, and makes library resources more visible on the Internet by distributing data across a growing number of partner services and Web technologies.

.

BHL Portal Usage

See attached PDF from Google Analytics for details.  Some highlights for the period.

292,304 visits

137,900 unique visitors

6.55 minutes average time on site.

The top referrers were Google, direct (i.e. none) and Tropicos.

1,053,401 EOL species pages have links to BHL texts. Of these EOL species pages, 792,107 have no other content than links to the BHL.

Gemini (user feedback system): Please see the attached report.  This will become a regular component of the S&D reporting.

CiteBank statistics.  This is the first quarter to report these and the final form may change slightly as we evaluate the best reporting data.

40 registered users

71,533 bibliographic citations

19,127 links with pdfs

52,426 not directly pdfs

Scientific – Professional Outreach:

'Biodiversity Heritage Library: Process & Progress' by Phil Cryer (MOBOT), Scripting Life: the science behind ViBRANT January 20-21, 2011 - Paris, France

“Biodiversity Heritage Library and JSTOR Plant Science,” Chris Freeland, 4th Annual Global Plants Initiative Meeting in Panama

Engaging New Audiences in New Ways: The Biodiversity Heritage Library. Martin R. Kalfatovic. Encyclopedia of Life Orientation. National Museum of Natural History, Smithsonian Institution. 31 January 2010. Washington, DC.

Open Scientific Digital Libraries: The Biodiversity Heritage Library." Martin R. Kalfatovic. Digital Libraries for the Maghreb. Fulbright Academy of Science & Technology. 24 January 2010. Washington, DC.

New Testimonials:

Monday, Jan. 31, 2011
From: Torben Larsen, via Gemini [mailto: torbenlarsen@btinternet.com]
I would just like to say how much I value the BHL. I am in the process of writing a monograph on the African Hesperiidae. Time and time again it is necessary some piece of obscure literature ... and I get it in no time flat rather than waiting till I get the Museum library - and a PDF to boot. Thanks and congratulations to a wonderful resource. Sincerely, Torben B Larsen Dr scient, cand. polit 

January 28, 2011
Eye for Science Blog: BHL, What a Find!
What a resource! I just discovered the Biodiversity Heritage Library - an online, open-access library that has digitized over 32 million pages of taxonomic literature from 45,000 books! Cha-CHING! Bookmarked. And just to give you a little taste of the deliciousness that awaits, I’m including some snappies from Dumeril’s Erpétologie générale, ou, Histoire naturelle complète des reptiles from the Smithsonian Institution’s Libraries. Talk about making science accessible. It’s no exaggeration to say that this type of image is what got me interested in scientific illustration in the first place. Now I can scroll through these old tomes on my computer?! Now we do a dance of joy!!

Friday, Jan. 28, 2011
From: David Leslie, via BHL gmail [mailto: DMLchip@aol.com]
Dear Grace:
Very nice to hear from you, and by all means, feel free to use the quote below! Indeed, I am very faithful and regular user. Just yesterday, a colleague (actually the Editor of Mammalian Species, with whom I work very closely) wanted to locate a publication on Siberian martins published in 1855. The citation from a contemporary paper looked odd to me, but with my growing familiarity with titles on BHL, I was able to find the series and paper and clean up the reference in about 10 minutes! Would have taken weeks just a few short years ago! I have also been helping with a large review of the bovids (hollow-horned oxen, antelopes and such) and have had to locate all of the original papers describing many of the species. Quite literally, this project would have taken years without BHL!! Lastly, I have been so pleased with the growing "coverage" of BHL that I find on Google searches, for example!
Keep up the GREAT work; many of us are indebted to all of you working on this important project!
Cheers,
Chip (David) Leslie

Tuesday, Jan. 25, 2011
From: 
Kristen L. Metzger
Director, Library & Information Services CSA International
8502 SW Kansas Avenue
Stuart, Florida 34997 USA
" These big government and oil company contracts are keeping me very busy. This job I’m just finishing up involved building a database of 10,000 citations/abstracts related to the eastern seaboard and acquiring the 3000 documents regarded as high priority. I can’t begin to tell you how much I used your Biodiversity Heritage Library – very cool.
See you in Alaska. Cheers, Kristen

Wednesday, January 19, 2011
From @BioInFocus (Morgan Jackson) via Twitter:
http://twitter.com/#!/BioInFocus/statuses/27883924831084544
Dear @BioDivLibrary, I <3 you! #makingtaxonomyeasier

Friday, January 14, 2011
From Charlotte Sleigh, via Gemini [mail to: c.l.sleigh@kent.ac.uk]
I just want to say what a fantastic resource the BHL is. I'm a historian of biology and I use it a great deal for my own research, plus recommend it to students. Thanks so much for this brilliant archive. 

Monday, January 10, 2011
From Pasi Sihvonen, via Gemini [mail to: pasi.sihvonen@helsinki.fi]
Dear Sir/Madam, I just wanted thank you very much for the excellent service you provide! The service has given me access to old literature, which was earlier inaccessible to me. It has made it so much easier and faster to work with old publications, I am so excited! Keep up the good work! Best regards, Pasi ----------------------------------------------- Pasi Sihvonen, PhD Head of Services, international research funding unit Research and Innovation Services University of Helsinki P.O. Box 33 (Yliopistonkatu 4) FI-00014 University of Helsinki, Finland Tel. +358 50 415 0236 pasi.sihvonen@helsinki.fi http://www.helsinki.fi/university ----------------------------------------------- 

Wednesday, January 5, 2011
From Ed Gilland, via Gemini [mail to: egilland@howard.edu]
Hello, and first off, thanks for all the fantastic scans of classic biology literature. The BHL collections seem to be the only ones with the foldout plates done properly. Kudos!
Commentary on desire for BHL to re-digitize content already available via Google or Hathi Trust

date Thu, Dec 30, 2010 at 12:43 PM
subject Re: Biodiversity Heritage Library Feedback

Hi Bianca,
Re: Kirkman's "The British bird book". Sorry about that. I usually check to see if BHL has a book before entering a scanning request. Guess I got lazy. Thanks for the head's up.
Re: Hathi Trust and Bradburn's "British Birds: Their Successful Management in Captivity". I'm all too familiar with Hathi Trust (it's where I found Bradburn's book to begin with!) and I try NOT to use them if there's another source. 

First off, one can't download anything in Hathi save in PDF format and that can only be done via the time-intensive method of one page at a time. Second, I've found that pages are all too often either missing or out of order. Third, one can only go through a document a single page at a time. No flip-book. No multi-page view. Fourth, their books are scanned by Google and Google tends to do an awful job of it. Not so much with text pages (those are generally okay), but when it comes to illustrations and plates, particularly color plates ... Ugh! Blurred. Or over-colored. Or under-colored. All too often de-colored. All this and/or amputated. (i.e. the front-piece plate in Bradburn's "British Birds" is missing the entire top half!). 
Anyway, thanks for the notices.
Arlene Rosenthal

Monday, December 13, 2010
[via BHL gmail acct]
Dear Grace:
So kind of you to respond with such detail (and Volume 5 is also important to me ;-p) ! I wasn't expecting any response, but should have, given the beautiful job you all do with the Biodiversity Library--it is just an awesome online resource! The absolute best of its kind! I just love the feature allowing a user to download selected pages of a lengthy tome and receiving (so darn promptly) a pdf of the pages requested!

I have been doing a lot work with the nomenclature of large mammals in the 1800s over the past 4 years, and the unbridled ease of finding material online has expanded exponentially to the point that I rarely have to use our interlibrary loan services for papers pre-1923! For me, the Biodiversity Library is always my first stop in any search, and much more often than not, I find exactly what I need!
You and your colleagues are very much appreciated! Happy Holidays coming! 
David Leslie
Unit Leader/Professor
Oklahoma Cooperative Fish and Wildlife Research Unit
Oklahoma State University


Friday, December 10, 2010
[via BHL gmail acct]
Thanks very much Grace – looking forward to the 1860s being done!
Love this service, by the way. BHL is a terrific resource and getting better all the time.
Mark Hutchinson
Senior Researcher, Herpetology
South Australian Museum

Tuesday, December 7, 2010
[via BHL gmail acct]
Dear Bianca
Thank you very much for your reply.
I am a researcher in molluscan palaeontology, in which we need to consult original descriptions for taxonomy. BHL is the best research tool I could hope for. May it continue to grow.
Many thanks
Bernie Landau