Seed & Nursery Catalog Digitization

January 21, 2014 conference call meeting notes

Attending:  John Mignault (NYBG), Andrew Tschinkel (NYBG), Michael Cook (Cornell), Dan Stewart (Cornell), Marty Schlabach (Cornell)

Agenda

Introductions

What has been done?

NYBG

Cornell

NAL (see Dec 29, 2013 email from Stan Kosecki)

Prioritization and coordination of selection for scanning?

McCaw at NYBG

Seed & Nursery Catalog Collection in BHL

Add all NAL catalogs from IA?

Copyright

Cataloging

Meeting schedule

Introductions

Marty Schlabach—Food & Agriculture Librarian, liaison to several academic depts

Cornell rep to BHL, is Cornell lead on this IMLS project

Michael Cook—Mann Library Head of Collection Development & Digital Collections Libn

Dan Stewart – MLIS student at SUNY Buffalo and spring semester intern on this project at Mann

John Mignault – NYBG Systems Libn, BHL Tech Advisory Group, Coordinator of NYBG digital projects

Andrew Tschinkel – NYBG Digital Imaging Technician, working on NEH grant project

(Paul Silverman --  soon back on-board at NYBG, not in attendance today)

Cornell update

Haven’t yet scanned any seed and nursery catalogs

Marty has met with several staff and faculty gathering feedback on selection priorities,

Taxonomist:

Thematic e.g. corn, oaks, grapes, apples

Synoptic picture, e.g. 10 catalogs of each year for 100 years

Taxonomist:

William Bull, British firm

Start with those of systematic value

Would be willing to review collection to select

Order of languages: English, Dutch, German, French

Continuous runs important

Heirloom Gardening:

1) Oldest, US-based, English lang, national, kitchen garden rather than ornamental

2) Smaller, regional/local firms

Catalog user assistance staff:

Local—Geneva, Rochester, NYC

Salesman’s plate books, flip books

NYBG update

NEH grant

Grant supports cataloging whole collection, mainly as serials

Supports digitizing 1,700 catalogs

970 digitized, 700 now in Mertz Digital Collections

Started with alpha list from catalogers

Switched to several prominent catalogs;  Dreer, Vick, Henderson, etc.

Recently scanned William H. Moon Co., and will be moving back to smaller catalogs

Currently putting digitized content into local Mertz Digital Collections (Content DM)

Will be pushing the catalogs and other relevant content to BHL when the capability is there

NAL

See email from Stan Kosecki  at end of notes

Prioritization and coordination of selection for scanning

NYBG has a spread sheet listing the items cataloged

Andrew adds notes logging the ones that have been scanned

He will provide a copy (sent 1/21)

Next direction for NEH scanning

Back to the alpha list continuing with ‘G’

Focusing on American

Marty will request list(s) from NAL

These two lists can be a starting point for comparison

Cornell can consider filling gaps in runs

Cornell can scan items not on lists

McCaw at NYBG

John and Don Wheeler are setting up and testing McCaw at NYBG

Will have feedback in the next month

Cornell quite interested in the outcome

Seed & Nursery Catalog Collection in BHL

Marty set up a ‘seed & nursery catalogs’ collection in BHL

Collection description drafted,  open to edits:

“This collection of seed and nursery catalogs was digitized primarily from the significant collections of New York Botanical Garden, Cornell University and the National Agricultural Library. The collection will continue to grow supported in part by a grant from the Institute of Museum and Library Services. We welcome suggestions of catalogs to consider for digitization and adding to the collection.”

Started by manually added catalogs already in BHL

There were a few from various non-BHL members until recently

Then many were ingested from NAL’s collection in IA:

https://archive.org/details/usda-nurseryandseedcatalog

Mike L. helped Marty bulk load into the collection all NAL catalogs that were tagged:

“Henry G. Gilbert Nursery and Seed Trade Catalog Collection”

NAL catalog collection in IA

4,003 items (Jan 22)

Mike indicated that he can add all

Shall we add all NAL catalogs from IA to BHL?

Agreed, and Marty will contact Mike about:

Automating the process of bulk loading to BHL

Automating the process of bulk loading to the ‘seed & nursery catalogs’ collection

Copyright

NYBG & Cornell agreeing to focus on public domain

US publications pre-1923

Except Burpee which lays claim to all their catalogs per NYBG

Non-US publications, various laws/regulations and considered separately

Cataloging

NYBG catalogs most as serials, listing holdings,

which also pulls items from the same company together

NAL catalogs most as monos

Cornell has cataloged items in a couple of different ways

Large runs have individual record, holdings sometimes in record

Small runs are grouped alphabetically with others

Meeting schedule

Agreed to meet every two weeks for a while

Marty will set up meetings

From: Kosecki, Stan [mailto:Stan.Kosecki@ARS.USDA.GOV] 
Sent: Thursday, December 26, 2013 10:36 AM
To: Marty Schlabach
Cc: Murphy, Pat - NAL; Derr, Kay
Subject: RE: Follow-up question RE: Seed catalog meeting at NYBG on 10 July 2012

Hi Marty,

Melanie Gardner and Mike Esman brought to my attention your email from a few weeks ago. I am swamped and not as current on replies as I wish to be.

Congratulations to all applicants on being awarded the IMLS grant!

For now, contact me regarding coordination issues related to nursery and seed trade catalogs. I am Cc: my digitization colleagues, Pat Murphy and Kay Derr. Please copy them on your future email. This will help us to be timelier in our responses.

To clarify NAL numbers. As of today, NAL digitized 3,676 nursery and seed trade catalogs. We are moving forward at about 170 catalogs per month. Right now, you can access our portfolio of digitized catalogs via https://archive.org/details/usda-nurseryandseedcatalog. Once we complete the reengineering process of our internal digital library platform, we will start delivering catalogs via NAL website. In parallel, we create bibliographic records in AGRICOLA and OCLC. As of today, we produced over 4,500 mostly monographic records.

In answer to your questions:

1.       Priorities

We are focusing the first phase of NAL nursery and seed trade catalogs digitization on specific needs. We are digitizing catalogs belonging to following facets:  Henderson, Women-owned, Mid-Atlantic, and long collection runs. Once we complete the long runs facet, we still will have over 90,000 catalogs to go.

2.       Coordination

I will gladly start a conversation with NYBG and Cornell on the overarching philosophy of and goals for the nursery and seed trade catalogs digitization project. I am eager to discuss how we can leverage each other’s work to minimize redundancy, mutually benefit from each other resources, and share final products.

3.       Cataloging

Most of our catalogs are cataloged as monographs. A number of years ago, we attempted to catalog them as serials. However, based on the process analysis and recommendations of folks who were involved in early phase of catalogs cataloging, we’ve decided to treat routinely each catalog as a monograph. We will make exceptions when there are very clear production advantages of treat a group of catalogs as a serial.

Stan

Happy New Year!

From: Marty Schlabach [mailto:mls5@cornell.edu] 
Sent: Thursday, December 12, 2013 11:14 AM
To: Kosecki, Stan
Subject: RE: Follow-up question RE: Seed catalog meeting at NYBG on 10 July 2012

Stan,

The joint IMLS proposal submitted by Missouri Botanical Garden (MoBot), NY Botanical Garden (NYBG), Cornell and Museum of Comparative Zoology (MCZ) at Harvard was approved and the project began on Dec 1.  NYBG and Cornell’s involvement is primarily to digitize seed and nursery catalogs and add to BHL.  MoBot will be scanning some seed lists.

At the time we were drafting the IMLS proposal, there were just a few seed and nursery catalogs in BHL.  Now there are more than 1,500, thanks to NAL’s digitizing effort and the fact that NAL’s digital copies were put into Internet Archive, from which BHL harvested them (the metadata).  Congratulations on your progress.  It’s quite impressive.

As we move forward with our digitizing initiative, we want to determine our selection priorities and minimize duplication.  We will be coordinating that between NYBG and Cornell.  We want to coordinate that with NAL as well, since your relevant digital content is being integrated into BHL.

Who would be the contact person at NAL for this purpose?

We have questions such as:

--What are your selection priorities/policies for digitizing seed and nursery catalogs?

--Since you are already targeting additional catalogs to digitize, can we coordinate with that to minimize duplication?

--Who is cataloging the items?  It appears that you are cataloging each catalog as a mono, rather than treating them as serials, with a single record for a company and the individual catalogs as holdings of the serial.  (though I did find some treated as serials as well, with multiple years associated with one record.)

I’m sure there are other questions, but wanted to give you a sense of what we have in mind, so you could put me in touch with the right person/people.

All the best,

Marty

From: Marty Schlabach 
Sent: Monday, April 22, 2013 8:44 AM
To: 'Kosecki, Stan'
Subject: RE: Follow-up question RE: Seed catalog meeting at NYBG on 10 July 2012

Thanks Stan, that’s the article I had in mind.  If I remember correctly, you indicated at the meeting last year that nothing had transpired following that 1970s meeting, including the union catalog or inventory didn’t happen, right?

That’s great that you are moving forward with a seed catalog digitization project.  Where are your catalog records going?  Do they end up in OCLC, or just in the NAL catalog?  When you digitize the catalogs, how/where will they be accessible?  I understand that NAL is considering joining BHL.  Whether NAL joins or not, it would be great to have the digitized catalogs added to BHL, along with others being digitized by other libraries and create a digital repository of seed and nursery catalogs.  Please keep me/us informed.  I’m very interested in this.

Last fall NYBG and Cornell began discussing the possibility of the two of us working together to digitize some of our respective catalogs, and collaborating to reduce duplication.  As you probably recall, NYBG is already cataloging their whole collection and digitizing a portion their collection with support from an NEH grant.  The goal of the Cornell/NYBG proposal was to add what we digitized to BHL and approach IMLS for funding.  When we approached BHL leadership with our idea, they recommended that we talk with Missouri Botanical Garden, since they were already working on an IMLS proposal that included crowdsourcing and gaming with existing BHL content.  The main purpose will be to use crowdsourcing to correct OCRed text.  NYBG and Cornell were added to the IMLS proposal to create a somewhat different format of content, the seed and nursery catalogs.  Harvard Museum of Comparative Zoology, also a BHL member, was added, since they are already digitizing field notebooks, which adds yet another format of content for crowdsourcing, in this case transcription.  We expect to hear about the proposal in the Fall.

Look forward to hearing more about this effort at NAL.

Marty