Seed & Nursery Catalog Digitization Meeting

October 14, 2014

Attendees:  Michael Cook (Cornell), Kay Derr (NAL), Pat Murphy (NAL), Marty Schlabach (scribe) (Cornell)

Cornell Update:

Now have 18,800 pages of seed and nursery catalogs ready for scanning.  First shipment not yet returned from the scanner (Trigonix).  Have received questions from scanner about several hard-to-scan items and permission given to unstaple to enable scanning.

Marty had a conference call with Susan Lynch, the new systems librarian at NYBG, summarizing the seed and nursery catalog digitization project.  Great to have her on-board and on this project.

NAL Update:

Sent Holly a spreadsheet of the 19,000 records so far cataloged, an entry for each mono record.  Explained that this is the best they can do.  Have not been consistent in the field used for the firm name.  NYBG sent their authority records to Stan at NAL, which will hopefully aid NAL in cataloging.  Cataloging and scanning are proceeding year by year.  Since the file was sent, NAL has now cataloged 20,000 items, through 1917.  Scanning is through 1901.  10,651 items now in IA.  BHL Seed & Nursery Catalogs collection now has 10,483 volumes, the vast majority of which are from NAL.

NAL is now an affiliate member of BHL.  Chris Cole will be the NAL rep to BHL.  Pat and Kay will have their first meeting with Chris this week, and have questions for him.  Such as, does BHL update metadata, when NAL corrects or adds metadata to an IA record?  (Scribe’s comment:  it’s great having NAL on-board with BHL.)

Marty noted that NAL has scanned seed and nursery catalogs that were published later than 1923 and inquired about NAL’s copyright policy.  NAL searches the web to see if the firm is still in business and if not found, considers the company defunct and feels comfortable scanning their catalogs.

NYBG Update:

No one from NYBG in attendance.  Marty reported that Susan Lynch has sent Holly a spreadsheet listing the firms that NYBG has cataloged.  Will need to do more work to note which ones have been scanned.  Holly now has spreadsheets from NYBG, NAL and Cornell, and when she returns from vacation will begin merging the files and matching up the firm names, so we can begin identifying our overlapping and unique firms and holdings.

Discussion:

NYBG and Cornell have been considering the creation of an IA seed and nursery catalog collection, as a place to put both institution’s scanned content.  This could semi-automate the process of adding them to the sub-collection in BHL, since Mike Lichtenberg has already developed a process for moving all the NAL seed and nursery catalogs from their IA sub-collection to the BHL sub-collection.  Marty didn’t think that NAL would want to have NYBG and Cornell add their digital content to NAL’s IA sub-collection, but Pat or Kay will check with Stan.  Another possibility would be for NAL to put their seed and nursery catalog in both their IA sub-collection and a sub-collection shared with NYBG and Cornell.   Marty has started investigating what it takes to set up a sub-collection in IA and also to how many sub-collections a particular item can be added.