Seed & Nursery Catalog Digitization

IMLS BHL Purposeful Gaming Project

Meeting Notes

December 9, 2014

Attending:  Kay Derr, Pat Murphy, Holly Mistlebauer, Michael Cook, Marty Schlabach (scribe)

Comparing the holdings lists of NYBG, Cornell and NAL  --  Holly

Each library has taken different approaches to cataloging, making it difficult to compare holdings and which is necessary to minimize duplication of scanning effort.  Holly received spreadsheets representing the catalog records for seed and nursery catalogs from each of the 3 libraries.  NYBG’s and Cornell’s lists represented all their holdings.  NAL is cataloging their collection in chronological order, and not yet complete.  Their report/list was through 1916 or 1917.  They expect to complete their cataloging of all the pre1923 catalogs by mid to late January, at which time NAL will send an updated list to Holly and she will update the comparison.

Holly used Google Refine to find firm names that were likely the same firm.  She was able to group all the records for items from the same firm.  That way we are able to see if catalogs from a given firm are held by one, two or three libraries.  Cornell and NYBG can now continue scanning by targeting the firms for which their holdings are unique among the 3 libraries, and avoid duplication.  That would be followed by finding unique holdings within firms that are held by more than one library.

NAL requested a copy of the resulting list which Holly has supplied.  NYBG also interested, but since Susan Lynch was not on today’s call to see the demo and explanation, Holly will arrange a time to show Susan and then provide a copy of the resulting report/list.

Cornell Update

Two shipments have gone out to Trigonix, Cornell’s scanning vendor.  5,000 pages in the first shipment, which deliberately included a wide diversity of seed and nursery catalog examples, for the vendor to quote a price.  Cornell had a preliminary estimate from them of $.27/page, and their quote following this sample of 5,000 pages is $.275.  A very acceptable price.  The second shipment of 10,000 pages has gone out, with another 15,000 pages prepared and ready to go out, after the first shipment’s images are received.  Following that shipment, Cornell will begin selecting firms/catalogs that are determined to be unique, based on Holly’s work mentioned above.

Marty has been invited to give a presentation to the Heirloom Gardening Symposium at the Genesee Country Village and Museum in Feb 2015 about the online seed and nursery catalog collection being built.

NYBG Update

No update available.

NAL Update

Have cataloged 17,000 catalogs and 11,800 catalogs have been scanned and are in IA.  A significant portion are also in BHL.  Have cataloged through 1920 and scanned through 1903.

NAL will eventually put all their scanned catalogs into the NAL repository, but it’s not ready at this point.

Marty asked about the Gilbert Catalog Collection name showing up first in some BHL records, which makes viewing the ‘author’ or firm name problematic.  He will provide examples.

2015 Meeting schedule

Those present agreed that the current meeting time of 11am on the 2nd Tuesday of the month works.  Will need to confirm with Susan Lynch, NYBG.