Seed & Nursery Catalog Digitization

IMLS BHL Purposeful Gaming Project

Meeting Notes

April 14, 2015

Attending:  Andrew Tschinkel (NYBG), Susan Lynch (NYBG), Pat Murphy (NAL), Kay Derr (NAL), Marty Schlabach (CUL), Holly Mistlebauer (CUL)

Cornell Update  --  Marty

--Scanning catalogs and processing via Macaw continues.  As of today, 112 catalogs in IA, and the usual lag between adding to IA and ingest into BHL.

--Garden Stories publicity campaign a great success.  Gave terrific exposure to the project and seed & nursery catalogs now available via BHL, most of which were scanned by NAL.

--Marty will propose giving a Purposeful Gaming talk at the Council on Botanical and Horticultural Libraries annual meeting in June Seed Savers Exchange in Iowa.  Hope to have a game for attendees to try out, and catalogs to transcribe.

--Cornell now has in-house scanning workflow and funding in place for special collection materials requested for BHL, and that will also allow us to scan fragile, valuable or other seed and nursery catalogs that we don’t want to send to an external scanning vendor.

--Holly & Marty will be attending the Purposeful Gaming face-to-face meeting at MOBOT on May 12.

--Marty and GIS colleague Keith Jenkins used sample NY seed and nursery firm data to map their locations in NYS, and changing by the dates of catalogs we have access to.  http://cdb.io/1ItFgbE .  This is just a ‘proof of concept’, there is a limited number of firms included and not the end product in mind, but sort of a cool start.

NYBG Update  --  Andrew, Susan

--Have suspended digitizing, reached limit of IMLS funds.

--Finished processing all with Macaw.

--Susan will be attending the Purposeful Gaming fact-to-face meeting at MOBOT on May 12.

--Of the catalogs scanned earlier with an NEH grant, all are in Mertz Digital.  A few have been added to BHL, but hard to determine gaps with Cornell and NAL still scanning.

NAL Update  --  Pat

--Actively scanning, 14,000+ at this point through 1908.  Scanning at a rate of about 1 publication year/month.

--30,000 seed and nursery catalogs cataloged through 1924.

Scanning non-US catalogs

--NAL scanned a few, based on requests, but not systematically.

--NYBG scanned some on previous grant.  Have not added them to BHL, waiting on Cornell for copyright guidance for non-US publications.  Have added them to Mertz Digital.

--Cornell hopes to start scanning non-US, if we can get clear guidance on copyright for each country.

--Susan reported that she has ‘darkened’ some titles in IA, it’s fairly easy, if we put something up that is later requested to be removed.

Sharing copyright permissions

--After discussion and brief review of BHL’s policy and permissions form, it was agreed that it seemed reasonable to follow the same for seed and nursery firms & catalogs.  Pat will ask Martin Kalfatovic and Bianca Crowley, and copy us, confirming this approach is ok.

Next meeting

Cancel.  Scheduled for May 12, which conflicts with the Purposeful Gaming face-to-face meeting at MOBOT