Seed & Nursery Catalog Digitization

IMLS BHL Purposeful Gaming Project

Meeting Notes

August 4, 2015

Attending:  Pat Murphy (NAL), Kay Derr (NAL), Holly Mistlebauer (CUL), Marty Schlabach (CUL), Susan Lynch (NYBG)

Cornell Update  --  Marty

Scanning pace has increased now that Cornell is focusing on catalogs from the UK.  Since neither NYBG nor NAL have scanned significant numbers of non-US catalogs, the time-consuming effort required to minimize duplication can be skipped.  Only pre-1923 are being scanned.  Shipment 5 has been sent to the scanning vendor bringing the total catalogs to 880 sent for scanning or 40,158 pages.  Shipment 6 is being prepared with an additional 95 catalogs and 10,780 pages ready to go out the door, bringing that total to 975 catalogs and 50,938 pages.  Of the catalogs scanned, 434 have been structured and sent to IA via Macaw and are now in BHL.

A question was raised about whether Cornell is using the same pre-1923 public domain date for other published material from UK.  The answer is no.  For monographs with one or few authors, Cornell tries to determine the death date of the author(s) and if 70 years since the author death have passed, it is considered in public domain.  In the case of serials, all authors’ death dates would need to be determined and since that’s not reasonable to do, Cornell is using a rule of thumb that a publication date of pre-1875 puts the item in public domain anywhere.  This is a moving date, since it has to do with the average projected death date of authors.

Marty also mentioned visiting the History Center of Tompkins County, the local county historical society to look at an 1860s catalog from the Jacksonville Nurseries, a nearby small town.  This catalog is not represented in Cornell’s collection nor has it been found in any other large catalog collection.  Archives staff also brought out several other seed and nursery catalogs in their collection and Marty found 7 total not found in Cornell’s collection.  This discovery leads one to want to check other local and regional collections for more unique seed and nursery catalogs.

NYBG Update  --  Susan

NYBG has not been scanning seed and nursery catalogs for the last 6 months, since they already have already completed their agreed-to scanning for the Purposeful Gaming project.

NAL  --  Pat

Internet Archive has scanned 16,539 catalogs so far from NAL’s collection.  Scanning chronologically, they are through 1912.  Catalogers have cataloged 19,112 catalogs and are currently working on 1927, cataloging about 1,900 per month.  Are reviewing post-1922 catalogs looking for copyright statements and checking the Stanford database for renewal.  NAL will likely continue scanning post-1922 materials unless determining an item is not in public domain.  NAL is also reviewing earlier dates of the collection that have already been scanned and have found some 19th century catalogs that were missed, which will be scanned either by IA or by NAL’s own staff.