Seed & Nursery Catalog Digitization

IMLS BHL Purposeful Gaming Project

October 13, 2015

No Meeting, Email Updates provided

NAL Update (Pat Murphy)

NAL’s totals as of the end of September.

For fiscal year 2015:

7,314 digitized

19,088 cataloged

Grand totals:

18,126 digitized

39,462 cataloged

We are currently cataloging 1930s catalogs.  Internet Archive is finishing up the 1914 catalogs.  Next, they will capture about 260 catalogs from 1901/1902 that had been pulled for a special project during the time we were processing that section of the collection.

For FY16, we plan to catalog and digitize at about the same pace.

Cornell Update (Marty Schlabach)

Cornell has sent to the scanning vendor on Sept 4 the final IMLS-supported shipment of seed & nursery catalogs, a total of 1,067 catalogs and 58,452 pages, meeting our adjusted target for the grant.  Of those 1,067 catalogs, 576 have been structured in Macaw, added to IA and ingested by BHL.  We continue to process the images as they are returned from the scanning vendor and cataloging is completed.

Separate from the grant project, I recently received from Portugal a request for 19th century Portuguese nursery catalogs, but Cornell does not have any.  But, it’s interesting the continued or increasing interest in and use of seed and nursery catalogs.