Seed & Nursery Catalog Digitization

IMLS BHL Purposeful Gaming Project

Meeting Notes

November 10, 2015

Attending:  Pat Murphy (NAL), Andrew Tschinkel (NYBG), Holly Mistlebauer (CUL), Marty Schlabach (CUL)

Cornell Update

Cornell sent to the scanning vendor the final shipment for the IMLS grant on Sept 9.  Total of 1,067 catalogs and 58,452 pages.  Scanning is now complete and structuring in Macaw and uploading to IA is continuing.  So far, 655 items have been sent to IA and ingested by BHL.  Structuring will continue at the same pace as the past several months.  Some of these will require catalog records to be created and that process is in place.

A question was raised asking for an estimate of the percentage of pre-1923 in Cornell’s collection that this represents, but Marty doesn’t have any idea, other than it is a very small percentage.  Cornell was only selecting catalogs to scan from firms that neither NYBG nor NAL have scanned or planned to scan.  Cornell has many catalogs that will not be scanned to avoid duplication of effort.  In an effort to speed up our output, we choose to switch from American firms to pre-1923 catalogs from British firms, since neither NYBG nor NAL have scanned many non-US catalogs.

NYBG Update

NYBG completed scanning seed and nursery catalogs for the IMLS grant more than a year ago, and have only scanned one specially requested catalog since.  It was a catalog from a Japanese firm that was mostly in English with some portions in German.  That one was not tagged in a way to be added automatically to the seed and nursery catalogs sub-collection in BHL, but that can be done in the BHL Admin module.

NAL Update

NAL continues cataloging and scanning at the same rate.  During fiscal year 2015 (which ended Sept 30), NAL scanned 7,314 catalogs, proceeding chronologically and now through 1913.  Also during FY 2015, NAL has cataloged 19,088 catalogs, now into the 1930s.  Cumulatively, NAL has digitized 18,126 and cataloged 39,462 seed and nursery catalogs.  They expect to continue scanning post-1922 when no evidence of copyright renewal is found.

It was also reported that NAL has a new director, Paul Wester, formerly of National Archives & Records Administration.  The library reports to former NAL director Simon Liu in his new role in the USDA.

NAL has renovated a new space for digitization, a former microform storage space.  Digitization initiatives in addition to seed and nursery catalogs include USDA publications and soon items from the rare book collection.  Currently, IA is the home for all of the digital content from these projects.

Next Meeting

This month brings with it the end of the 2 year IMLS Purposeful Gaming project, through which NYBG and Cornell received funding to scan a portion of their seed and nursery catalog collections.  We will meet at least one more time next month at our usual time, Tuesday Dec 8 at 11am.